| THE PEOPLE’S COMMITTEE OF HO CHI MINH CITY -------- | SOCIALIST REPUBLIC OF VIETNAM Independence - Freedom - Happiness --------------- |
| --- | --- |
| No: 26/2011/QĐ-UBND | Ho Chi Minh, May 14, 2011 |

DECISION

PROMULGATING PLAN FOR IMPLEMENTATION OF THE RESOLUTION OF THE IXTH PARTY CONGRESS OF HO CHI MINH CITY ON REDUCING FLOODING IN PERIOD OF 2011-2015

PEOPLE’S COMMITTEE OF HO CHI MINH CITY

Pursuant to the Law on Organization of the People’s Councils and the People’s Committees dated November 26, 2003;

Pursuant to the Resolution of the resolution of the IXth party congress of Ho Chi Minh city;

Pursuant to Action Program No. 13-CTrHĐ/TU dated March 16, 2011 the Party Committee of Ho Chi Minh city on implementation of the resolution of the IXth party congress of Ho Chi Minh city on reducing flooding in period of 2011-2015;

At the request of the Central Executive Program wetland protection in Report No. 1402 / TTr handicrafts December 13, 2010 Draft Implementation Plan Party Congress Resolution Ninth city on flood reduction program the period 2011 - 2015;

At the request of the Steering center of flood control in the Report No. 1402/TTr-TTCN dated December 13, 2010 Drafting the Plan for the implementation of the Resolution of the resolution of the IXth party congress of Ho Chi Minh city on reducing flooding in period of 2011-2015,

HEREBY DECIDES:

Article 1. To enclosed with this Decision the Plan for implementation of the Resolution of the IXth Party Congress of Ho Chi Minh city on reducing flooding in period of 2011-2015.

Article 2. The heads of departments in Ho Chi Minh city, the Presidents of the People’s Committees of districts, the heads of agencies and units directly managed by the city base on their assigned functions, tasks, and the contents of this Plan to formulate specific programs and plans in order to implement effectively the program of reducing flooding in period 2011-2015.

Article 3. This Decision takes effect after 10 days from its signing.

Article 4. The Chief officers of People’s Committee of Ho Chi Minh city, the Director of the Steering center of flood control of Ho Chi Minh city, the Heads of departments in Ho Chi Minh city, the Presidents of People’s Committee of districts, the Heads if agencies and units directly managed by the city shall be responsible for the implementation of this Decision./.

|  | FOR THE PEOPLE’S COMMITTE THE PRESIDENT Le Hoang Quan |
| --- | --- |

PLAN

FOR IMPLEMENTATION OF THE RESOLUTION OF THE IXTH PARTY CONGRESS OF HO CHI MINH CITY ON REDUCING FLOODING IN PERIOD OF 2011-2015 (enclosed herewith Decision No. 26/2011/QĐ-UBND dated May 14, 2011 of People’s Committee of Ho Chi Minh city)

In order to implement effectively the Action Program No. 13-CTrHĐ/TU dated March 16, 2011 the Party Committee of Ho Chi Minh city on implementation of the Resolution of the IXth Party Congress of Ho Chi Minh city on reducing flooding in period of 2011-2015; People’s Committee of Ho Chi Minh city formulates the following specific plan:

I. OBJECTIVES

1. General objectives:

Focus on basic solving flooding in the central area (approximately 100km2); control and prevent new flooding in remaining 5 areas (approximately 580km2); resolve fundamentally flooding caused by rainwater in 5 periphery areas and the remaining area of ​​the city in period of 2016 – 2020.

2. Specific objectives:

Period of 2011-2015:

Basically solve flooding caused by rainwater and tides in the central area (100km2 with approximately 3.3 million people); strive to eliminate the existing flooded points due to rainwater, which in turn, reduce flooding in the northern area of Tau Hu, Tan Hoa - Lo Gom (districts 6, 11, Tan Phu, Binh Tan, a part of Districts 6, 8, Binh Thanh), remedy flooding caused by construction, limit new flooded points.

For the remaining 5 drainage areas (580 km2 with approximately 3,4 million people), strive to reduce 70% of flooded points due to rain, 50% flooded points due to tides; control and prevent new flooded points.

Period of 2016-2020:

Basically solve flooding due to rain in 5 drainage areas and the remaining area of ​​the city in 2020.

Extend the area of protection against flooding outside the scope of study of the planning for drainage (District 12, Hoc Mon, Cu Chi, Binh Chanh).

Period of 2021-2025:

Solve thoroughly flooding due to rain; solve basically flooding due to inundation and tides, taking into account the phenomenon of sea level rise in the future across the city.

II. PRIMARY TASKS AND SOLUTIONS

1. Improve the quality of the planning and the effectiveness of management of the planning and construction:

Review and adjust the planning towards integrated planning in order to minimize the risk of flooding, which is the basis for priority investment orientation in each stage, in order to proactively adapt to climate change, sea level rise, improve the effectiveness of management of tasks of flood prevention in the city based on the planning approved by the Government and the research results of scientific institutions in Vietnam and abroad. Focus on planning the rainwater drainage system and development of technical infrastructure by issuing provisions on high-level control of construction foundation, focusing on perfecting surface, increasing area of verdure, grass cover in the existing area inner the city (13 old districts), developed areas inner the city (6 new districts), agricultural residential areas and new urban areas in five districts in the right bank of Saigon - Nha Be Rivers under the closed dyke system.

Strengthen the management of land, ensure that water surface area, waterway system can meet the requirement for drainage and flood prevention; intensively manage agricultural land, arrange the axis of verdure, water surface (width from 50 – 800 meters) to form three ecological belts (width from 2,000 - 3,000 meters) along the banks of Saigon, Dong Nai, and Nha Be rivers.

- Strictly manage the leveling and construction of works on public rivers, canals, lakes; make the overall planning for the system and construct reservoirs in suitable areas, reducing the increase in flow to assist drainage; ensure the area of ​​flooded areas in places that have low topography, waterway area and create ​​urban landscape.

- Calculate the norms of rain, tides, floods, ecology when preparing documents of projects, designs so that the adaptation to climate change shall be guaranteed when such projects are put into use. Strengthen the urban management, formulate appropriate regulations on offset the leveled water surface area and prevent runoff coefficient increases; stipulate strict sanctions to protect effectively drainage pit systems, waterways, buffer zones, water regulation area.

Study and develop mechanisms and policies to meet the requirements for elimination and reduction of flooding:

- Prioritize ODA for investment and development of systems of drainage, collection of wastewater, works of reservoir, dykes and tide control culverts; have plans for investment budget to develop the drainage system, tidal control system.

- Encourage and mobilize capital from investors in Vietnam and abroad to build drainage systems, especially wastewater treatment plants.

- Develop a roadmap of increasing water drainage fees to ensure that in 2015, water drainage fees can meet the requirements for management and operation of water drainage systems, water environmental treatment.

2. Improve the effectiveness of implementation of solutions to reduction of flooding, gradual elimination of flooding in the area.

Focus on directing and handling efficiently the existing flooded points; actively cooperate with Central Ministries and departments to solve quickly difficulties and obstacles to accelerate the completion and use of the project of rain water drainage, tide control; adopt technical solutions for urgent drainage, dredging the flow at the sluice gates, canals trespassed in order to reduce flooding.

Resolutely penalize illegal trespass in order to dredge canals and perform gentrification:

- Quickly complete the construction planning with the rate of 1/2000, determine the high edge, and determine accurately the protection corridors of rivers, canals to serve the clearance of illegal trespass.

Strive to implement basically the program of clearance of the slums on the canals as the basis for dredging, clearing drainage canals, and reducing water pollution at the end of 2014.

Essentially implement the program of gentrification along the banks of canals, creating appropriate space to increase the area of ​​the water regulating buffer zone and create urban landscape in period of 2012 - 2015.

- Develop specific regulations on the location of dikes, dikes used for traffic in waterway boundaries to facilitate construction, reinforcing and repair; limit trespass, protect the safety of dikes, and increase water storage capacity in case of rain, tides and floods.

- Focus on premises clearance, particularly compensation, assistance of relocation for people in the project of dikes, dredging of canals to serve water drainage; resolutely relocate trespass of canals, sluice gates, water drainage systems.

Promote measures of control the new flooded areas:

- Make planning for appropriate foundation, build adequate drainage systems, connect synchronously with the drainage system of the area for projects of urban development, development of new residential areas.

- Strengthen inspection, monitoring and strictly handle violations; remedy the trespass affecting the existing drainage system and flooding due to construction works.

- Continue to implement the plan for renovation and upgrading the old drainage system in the central area to connect synchronously with the new system; obdurate and destroy culverts which are no longer effective to remedy the run-down condition causing subsidence and re-flooding. Construct main axis drainage system in 5 remaining drainage areas and new urban areas, strictly handle cases of leveling, trespass of canals, sluice gates, drainage system in which infiltration surface area and rain water storage capacity are guaranteed.

- Study, develop regulations to offset leveled water surface area and prevent runoff coefficient increases; prescribe sanctions for violations in order to protect the drainage pit system, canals, buffer zones, water regulation areas; stipulate mechanisms and policies for development of water regulatory space in the projects of gentrification and urban development; continue to study and apply appropriate materials used for pavement, parks to avoid being concreted.

- Review and supplement the technology solutions of urban rainwater management; study to make planning of model water regulation area for some drainage areas in order to create the premise for widespread deployment in the area, in order to prevent and control flooding, proactively adapt climate change.

- Study and apply new technologies in the construction of works of drainage, works of canal and river bank protection such as dykes, embankments etc ... in order to ensure sustainability, high economic efficiency and urban beauty.

- Make plans for renovation and upgrading the drainage pit routes in order to solve flooding in urbanized areas (districts 5, 6, 11, 12, Binh Tan, Tan Phu, Go Vap, Binh Chanh) , complete the renovation and upgrading the drainage pit systems in Central, Western and Northern areas of the city.

3. Ensure the progress of implementation of programs and projects of flood prevention in the area:

Focus on directing to solve difficulties and obstacles in order to accelerate the completion of the projects of drainage and flood prevention in period of 2005 - 2010:

- Project of water environmental Sanitation in Nhieu Loc - Thi Nghe basin;

- Project of water environment Improvement in Ben Nghe - Tau Hu – Kenh Doi- Kenh Te canal basin in 1st and 2nd periods;

- Project of sanitation improvement and urban upgrading in Tan Hoa - Lo Gom basin;

- Project of drainage and pollution improvement in Tham Luong - Ben Cat – Rach Nuoc Len canals in 1st period;

- Project of drainage system in Nhum river and renovation of Ba Bo cannel;

- Project of dikes of the right bank of Sai Gon River from Vam Thuat (District 12) to Provincial Route 8 (Cu Chi) and the left bank of the Saigon River (from Binh Phuoc bridge to Cau Ngang canal, Thu Duc district).

Concentrate capital, promote the reform of administrative procedures in order to accelerate investment preparation and implementation of projects of dikes and tidal control culverts, dredging important drainage canals; projects of drainage and wastewater treatment in the Northern, Western, Southeast, Northeast, and Southern areas of the city:

- Construct the system of dykes at the right bank of the Saigon River (from Vam Thuat - Binh Thanh District to Kinh Lo, Nha Be District and from Provincial Route 8 to Ben Suc, Cu Chi district) and at the left bank of the Saigon River (from Cau Ngang canal - Thu Duc District to Thu Thiem - District 2). Build 7 large-scale tidal control culverts tidal and medium and small-scale tidal control culverts.

- Dredge important drainage canals, perform gentrification, and apply new technologies to protection of canal, river banks.

- Renovate, upgrade and construct drainage systems in order to develop synchronously, increase drainage capability for central area and a number of peripheral areas.

- Construct the system of drainage, wastewater collection for the wastewater treatment plant in basins of Tan Hoa - Lo Gom, south of Tham Luong, west of Saigon, Nhum river, Nhieu Loc - Thi Nghe, Thu Thiem new urban areas in District 2.

4. Strengthen association, cooperation in science - technology to serve eliminating and reducing flooding:

Develop mechanisms and policies, facilitating exchange and cooperation in science - technology with international organizations, non-governmental organizations, institutes and universities in order to meet the requirements for training of human resources in the field of urban drainage. Expand training majors at the vocational school in order to train specialized workers to serve requirements for management, operation, and maintenance of drainage systems and wastewater treatment plants.

Focus on studying and assessing the impact of climate change on economic- society; formulate integrated strategy in order to increase the ability to adapt and respond to flooding; improve the ability to monitor and forecast floods; study the mechanisms and solutions to improve the capacity of relevant organizations and the role of the community in the strategy of response, adapting to climate change, the impact of recharge of rainwater on the dynamic and quality of underground water, happenings of Saigon river bed, the ability to increase the capacity of drainage and erosion prevention, the ability to respond to rain events exceeding the design frequency due to climate change for the urban drainage systems ...

5. Improve the effectiveness and efficiency of State management for infrastructure systems of drainage, urban wastewater treatment:

Concentrate and uniform the management, improvement of the efficiency of state management of systems of water drainage, wastewater treatment, and works of tidal control in order to manage flooding caused by climate change.

Construct and complete database system of the drainage network based on digitizing and build the model of management according to the system of supervisory control and data acquisition (SCADA); formulate the strategy of management, operation, protection, expansion, and construction of drainage system; develop a roadmap for increase of drainage fee and environmental protection fee charged for domestic wastewater; effectively prevent new flooded points through the application of technology of management of canals, drainage systems, management tool of planning and construction to localize and protect buffer zones, the water regulation areas in the process of urbanization.

Develop mechanisms and policies to attract scientific staff, study and apply scientific advances, advanced technology of the world in order to improve the monitoring, forecasting, and proposing measures of responses , adapting to climate change.

Supplement the competence of the inspection bodies in handling administrative violations within the scope and functions of state management in drainage, prevention of urban flooding.

6. Promote the role of the Fatherland Front and politics - society organizations in propagandizing the people and monitoring the implementation of flooding management strategies in the area:

Promote the propagation, education of unionists, members, people to participate in effective implementation of the movement "For a clean and beautiful city"; cooperate with functional departments to regularly conduct the campaign of street cleaning, dredging of canals, environmental protection, protection of drainage systems in residential areas; monitor community in this field.

III. IMPLEMENTATION

1. Directors of departments, affiliates of People’s Committee of Ho Chi Minh city and Presidents of People’s Committee of districts graph thoroughly and formulate specific plans in accordance with the reality and political objectives of each unit and locality, along with the implemetation of the Plan for socio-economic development in 2011-2015 in order to implement effectively this Program; Direct and inspect the implementation of levels, departments, annually sum up partially and report the results to the People's Committee of Ho Chi Minh city.

2. The Director of the Department of Interior Affairs and relevant agencies advice, propose strengthen the organization of apparatus, personnel, training, retraining the capacity of cadres of the State management agencies, the Steering center of flood control, the management board of investment in construction of urban traffic works and the management Boards of the project of prevention of urban flooding.

3. The Service of Information and Communications and press agency of the city increase specialized pages, columns, documentaries, reportage of which theme is about propagandizing and raising the awareness, responsibility of community in implementing the legislation on environmental protection; promptly criticize violations, commend, and replicate typical activities.

4. The Steering Center of Flood Control is the standing body, being responsibility for regulating and ensuring the uniform implementation of this plan, periodical summarizing and reporting the results to the President of the People’s Committee of Ho Chi Minh city.

Departments and the People’s Committee of districts shall cooperate with the Steering Center of Flood Control to summarize and report to the President of People’s Committee of Ho Chi Minh city about any adjustments during the implementation ./.

APPENDIX 1

LIST OF PROGRAMS, WORKS FOR IMPLEMENTATION OF THE RESOLUTION OF THE IXTH PARTY CONGRESS OF HO CHI MINH CITY ON REDUCING FLOODING IN PERIOD OF 2011-2015 (enclosed herewith Decision No. 26/2011/QĐ-UBND dated May 14, 2011 of People’s Committee of Ho Chi Minh city)

| NO | DESCRIPTION | STEERING AGENCY | COORDINATING AGENCY | TIME |
| --- | --- | --- | --- | --- |
| 1. | Project of strengthening the management of land, ensuring that water surface area, waterway system can meet the requirement for drainage and flood prevention; strictly manage agricultural land, arrange green trees... form three ecological belts along the banks of the Saigon, Dong Nai, and Nha Be rivers. | the Service of Natural Resources and Environment | the Service of Agriculture and Rural development, relevant departments, and People’s Committee of Cu Chi, Hoc Mon, Nha Be, Thu Duc districts and districts 9, 12, 2, 7. | Third quarter/ 2011 |
| 2. | Project of management of the leveling and construction of works on public rivers, canals, lakes to ensure area of ​​flooded areas in places that have low topography, river area and create ​​urban landscape. | the Department of Planning - Architecture | Relevant departments and People’s Committee of districts | Third quarter/ 2011 |
| 3. | Completing the construction planning with the rate of 1/2000 (1), determining the high edge, determining accurately the protection corridors of rivers, canals to serve the clearance of trespass (2). | the Department of Planning - Architecture (2) the Services of Transport and the Service of Agriculture and Rural development | Relevant departments and People’s Committee of districts | second quarter/ 2011 so that districts can determine the size of clearance and dredging cannals |
| 4. | Making planning system of reservoirs in appropriate areas (1), creating design, and building a number of reservoirs in Thu Thiem Area (District 2), Northwest urban area (Cu Chi), Binh Chanh, district 12 in order to learn from technical experience (2). | The Steering Center of Flood Control | Departments and People’s Committee of districts | Fourth quarter/ 2011 (2) Second quarter/ 2011 |
| 5. | Formulating intergrated planning in order to minimize steadily the risk of flooding | The Steering Center of Flood Control | Relevant departments and People’s Committee of districts | Third quarter/ 2012 |
| 6. | Studying and develop mechanism and policies to encourage and mobilize capital from investors in Vietnam and abroad to build drainage systems, especially wastewater treatment plants. | Research and development Institute | Relevent departments | Third quarter/ 2012 |
| 7. | Formulate the plan to balance investment in development of drainage, flood protection infrastructure | The Service of Planning and investment | Relevant departments | Fourth quarter/ annually |
| 8. | Developing a roadmap of increasing water drainage fees to ensure that in 2015, water drainage fees can meet the requirements for management and operation of water drainage systems, water environmental treatment. | the Service of Finance and the Steering Center of Flood Control | Relevant departments | Fourth quarter/ 2010 |
| 9. | Focusing on directing and handling efficiently the existing flooded points; adopting technical solutions for urgent drainage, dredging the flow at the sluice gates, canals trespassed in order to reduce flooding. | The Steering Center of Flood Control | Urban Drainage Company Ltd. and People’s Committee of districts | The plan for implementation is formulated annually |
| 10. | Strengthening inspection, monitoring and strict handling violations; remedying the trespass affecting the existing drainage system and flooding caused by construction works. | The Services of Transport | The Steering Center of Flood Control, Urban Drainage Company Ltd. and People’s Committee of districts | The plan for implementation is formulated annually |
| 11. | Developing regulations on the location of dike routes in waterway boundaries to facilitate construction and repair; limiting trespass, protecting the safety of dikes, and increasing water storage capacity in case of rain, tides and floods. | the Service of Agriculture and Rural development | Relevant departments and People’s Committee of districts | First quarter/ 2011 |
| 12. | Studying and applying new technologies in the construction of works of drainage, works of canal and river bank protection such as dykes, embankments, etc ... in order to ensure sustainability, high economic efficiency and urban beauty (1). Submitting the project of manufacturing uPCV sheet pile (2) | The Steering Center of Flood Control | (1) the Service of Agriculture and Rural development, the Service of Science and Technology, the Services of Transport, the Service of Construction. (2) Sai Gon Industry Corporation | Third quarter/ 2011 |
| 13. | Focusing on directing to solve difficulties and obstacles in order to accelerate the completion of the projects of drainage and prevention of flooding in period of 2005 - 2010: | Investors of the projects | Relevant departments and People’s Committee of districts | Frequently |
| 14. | Concentrating capital, promoting the reform of administrative procedures (1) in order to accelerate investment preparation and implementation of projects of dikes and tidal control culverts, dredging important drainage canals; projects of drainage and wastewater treatment for the Northern, Western, Southeast, Northeast, and Southern areas of the city (2) | The Service of Planning and investment (2) The Steering Center of Flood Control | Relevant departments Steering Committee of administrative reform of Ho Chi Minh city | First quarter/2011 (2) December/2010 |
| NO | DESCRIPTION | STEERING AGENCY | COORDINATING AGENCY | TIME |
| 15. | Developing mechanisms and policies to facilitate exchange and cooperation with international organizations, non-governmental organizations, institutes, universities in science - technology | the Service of Science and Technology | the Service of Internal Affairs, the Service of Finance and the Steering Center of Flood Control | Third quarter/ 2011 |
| 16. | Formulate the plan for cooperation in studying scientific research topics in order to improve the ability to adapt and respond to climate change ... | the Service of Science and Technology | Vietnam National University, relevant departments | Second quarter/ 2011 |
| 17. | Project of concentrating and uniforming the management of system of water drainage, wastewater treatment and works of tidal control in order to manage flooding caused by climate change, contributing to creating a breakthrough in the direction, operation to prevent flooding in the area. | The Steering Center of Flood Control | The Service of Internal Affairs | First quarter/ 2011 |
| 18. | Project of building and improving database system of the drainage network based on digitizing and building the model of management and control SCADA system ... | The Steering Center of Flood Control | Vietnam National University, relevant departments | Second quarter/ 2011 |
| 19. | Supplementing the competence of the inspection bodies in handling administrative violations within the scope and functions of state management in the drainage, prevention of urban flooding. | The Service of Internal Affairs | The Service of Justice, the Services of Transport, the Service of Construction | December/2010 |
| 20. | Setting up the project: Promoting the propagation, educating people to participate in effectively implementation of the movement "For a clean and beautiful city"; increasing specialized pages, columns, documentaries, reportage of which theme is about propagandizing and raising the awareness, responsibility of community in implementing the legislation on environmental protection; promptly criticize violations, commend, and replicate typical activities. | The Steering Center of Flood Control | the Service of Information and Communications , Vietnamese Fatherland Front Committee of Ho Chi Minh City and organizations | Second quarter/ 2011 |

APPENDIX 2

SUMMARY OF CAPITAL REQUIREMENTS PER YEAR IN PERIOD OF 2011 – 2015 (enclosed herewith Decision No. 26/2011/QĐ-UBND dated May 14, 2011 of People’s Committee of Ho Chi Minh City)

| NO | CLASSIFICATION | NUMBER OF PROJECT | TOTAL INVESTMENT (Billion VND) |  | CAPITAL REQUIREMENT PER YEAR (BILLION VND) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 |
| A | RENOVATING, UPGRADING DRAINAGE SYSTEM | 159 | 9.523,296 |  | 367,721 | 1.133,786 | 1.517,860 | 2.527,133 | 3.976,797 |
| B | SYSTEM OF COLLECTION AND WASTEWATER TREATMENT PLANTS | 8 | 55.251,571 | 2.534,980 | 9.257,516 | 10.523,410 | 10.861,700 | 10.063,320 | 6.049,880 |
|  | LOANS | 5 | 30.149,830 | 2.534,980 | 5.067,570 | 5.523,410 | 5.861,700 | 5.063,320 | 1.569,880 |
|  | BUDGET CAPITAL | 3 | 25.101,741 |  | 4.189,946 | 5.000,000 | 5.000,000 | 5.000,000 | 4.480,000 |
| C | PROJECTS OF TIDAL CONTROL | 17 | 15.064,579 |  | 3.311,985 | 3.006,741 | 2.895,839 | 2.900,000 | 4.320,000 |
|  | TOTAL (A+B+C) | 184 | 79.839,446 | 2.534,980 | 12.937,222 | 14.663,937 | 15.275,399 | 15.490,453 | 14.346,677 |

APPENDIX 2A

RENOVATION, UPGRADING, AND DEVELOPMENT OF DRAINAGE SYSTEM IN PERIOD 2011-2015 (enclosed herewith Decision No. 26/2011/QĐ-UBND dated May 14, 2011 of People’s Committee of Ho Chi Minh City)

| NO | List | Location | current condition | Size | Total investment (billion VND) | Capital requirement per each (billion VND) |  |  |  |  | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2011 | 2012 | 2013 | 2014 | 2015 |  |
| RENOVATION OF DRAINAGE SYSTEM |  |  |  |  |  |  |  |  |  |  |  |
| 1. BASIN IN CENTRAL AREA |  |  |  |  |  |  |  |  |  |  |  |
| Renovating degraded, old drains which have high risk of collapse |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Renovating the drainage system on Hai Ba Trung street ( from Nguyen Thi Minh Khai to Me Linh square) | District 1 | Degraded arch culverts | - Length = 1300 meters - Installing culverts D1200 - Backfilling trench and re-asphalting pavements | 48,304 | 9,661 | 38,643 |  |  |  |  |
| 2 | Renovating the drainage system on Pham Ngu Lao street ( from Cong Quynh street to Nguyen Thai Hoc street) | District 1 | culvert D800 | - Length = 750 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 24,433 | 7,330 | 17,103 |  |  |  | Urgent |
| 3 | Renovating the drainage system on Pham Ngu Lao street ( from Nguyen Thai Hoc street to Pho Duc Chinh street) | District 1 | Degraded arch culverts | - Length = 50 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 21,133 |  | 4,227 | 16,906 |  |  |  |
| 4 | Renovating the drainage system on Nguyen Dinh Chieu street ( from Hai Ba Trung street to Dinh Tien Hoang street) | District 1 | Arch culvert B800 | - Length = 600 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 20,442 |  | 4,088 | 16,354 |  |  |  |
| 5 | Renovating the drainage system on Truong Quyen Street ( from Vo Thi Sau street to Dien Bien Phu street) | District 1 | Culverts D400, D800 | - Length = 280 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 7,833 |  | 1,567 | 6,266 |  |  |  |
| 6 | Renovating the drainage system on Mai Thi Luu – Nguyen Huy Tu street ( from Dinh Tien Hoang street to Nguyen Dinh Chieu street) | District 1 | Culverts D400, D800 | - Length = 350 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 11,414 |  | 2,283 | 9,131 |  |  |  |
| 7 | Renovating the drainage system on Nam Ky Khoi Nghia street ( from Nguyen Thi Minh Khai street to Ben Chuong Duong street) | District 1 | Degraded arch culverts | - Length = 1250 meters - Installing culverts D1200 - Backfilling trench and re-asphalting pavements | 46,372 |  | 9,274 | 37,098 |  |  |  |
| 8 | Renovating the drainage system on Dinh Tien Hoang street ( from Nguyen Dinh Chieu street to Vo Thi Sau street) | District 1 | Degraded arch culverts | - Length = 650 meters - Installing culverts D1200 - Backfilling trench and re-asphalting pavements | 24,101 |  | 4,820 | 19,281 |  |  |  |
| 9 | Renovating the drainage system on Dong Khoi street ( from Saigon river to Nguyen Du street) | District 1 | Degraded arch culverts | - Length = 1000 meters - Installing culverts D1500 - Backfilling trench and re-asphalting pavements | 44,413 |  |  |  | 8,883 | 35,530 |  |
| 10 | Renovating the drainage system on Cong Quynh street ( from Nguyen Thi Minh Khai street to Nguyen Cu Trinh street) | District 1 | Degraded culverts | - Length = 1000 meters - Installing culverts D1200-D2000 - Backfilling trench and re-asphalting pavements | 50,365 |  |  |  | 10,073 | 40,292 |  |
| 11 | Renovating the drainage system on Pasteur street (from Le Thanh Ton street to Ben Chuong Duong street) | District 1 | Degraded arch culverts | - Length = 900 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 30,711 |  |  |  | 6,142 | 24,569 |  |
| 12 | Renovating the drainage system on Tran Cao Van Street (from Mac Dinh Chi street to Hai Ba Trung street) | District 3 | Culverts D400, D500 | - Length = 300 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 10,269 |  |  |  | 2,054 | 8,215 |  |
| 13 | Renovating the drainage system on Ly Thai To street (from the house No. 106B to roundabout) | District 3 | culverts D500 | - Length = 500 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 14,026 | 4,208 | 9,818 |  |  |  | Urgent |
| 14 | Renovating the drainage system on Vo Van Tan street (from Cach Mang Thang 8 street to Cao Thang street) | District 3 | Culverts D400, D600 | - Length = 800 meters - Installing culverts D1000-D1500 - Backfilling trench and re-asphalting pavements | 30,174 |  |  | 6,035 | 24,139 |  |  |
| 15 | Renovating the drainage system on Do Ngoc Thanh street (from Nguyen Chi Thanh street to Tan Hung street) | District 5 | Degraded arch culverts | - Length = 300 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 8,891 | 2,667 | 6,224 |  |  |  | Urgent |
| 16 | Renovating the drainage system on Duong Tu Giang street ( from Tan Thanh street to Trang Tu street) | District 5 | Arch culverts [0,8x1,7]meters | - Length = 490 meters - Installing culverts D1200-D1500 - Backfilling trench and re-asphalting pavements | 24,459 | 7,338 | 17,121 |  |  |  | Urgent |
| 17 | Renovating the drainage system on Tran Nhan Ton street (from Hoa Hao street to An Duong Vuong street) | District 5 | culverts D600 | - Length = 590 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 17,425 | 5,228 | 12,198 |  |  |  | Urgent |
| 18 | Renovating the drainage system on Nguyen Trai street (from Tan Da street to Chau Van Liem street) | District 5 | Arch culverts [0,8x0,6]meters | - Length = 700 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 20,691 | 6,207 | 14,484 |  |  |  | Urgent |
| 19 | Renovating the drainage system on Nguyen Trai street (from Tran Phu street to Tan Da street) | District 5 | Culverts D400, D500, D600 | - Length = 700 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 20,691 |  | 4,138 | 16,553 |  |  |  |
| 20 | Renovating the drainage system on Nguyen Trai street (from Chau Van Liem street to Nguyen Thi Nho street) | District 5 | Culverts D400, D500, D600 | - Length = 1000 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 29,500 |  |  |  | 5,900 | 23,600 |  |
| 21 | Renovating the drainage system on Nguyen Trai street (from Nguyen Tri Phuong street to Nguyen Trai street) | District 5 | Arch culverts [0,8x1,4]meters | - Length = 350 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 11,948 | 3,584 | 8,364 |  |  |  | Urgent |
| 22 | Renovating the drainage system on An Duong Vuong street (from Tran Binh Trong street to Nguyen Van Cu street) | District 5 | Arch culverts [0,8x1,4]meters | - Length = 400 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 13,628 | 4,088 | 9,540 |  |  |  | Urgent |
| 23 | Renovating the drainage system on An Duong Vuong street (from Su Van Hanh street to Ngo Quyen street) | District 5 | Arch culverts [0.8mx1.4m]meters | - Length = 400 meters - Installing culverts D1000-D1200 - Blackfilling trench and re-asphalting pavements | 12,409 |  | 2,482 | 9,927 |  |  |  |
| 24 | Renovating the drainage system on Hung Dugong street (from Ngo Queen street Do Ngoc Thatch street) | District 5 | Culverts D400, D600, arch culverts (0.8x1.4) meters, (1.4x1.6) meters | - Length = 1140 meters - Installing 02 culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 75,018 | 15,004 | 60,014 |  |  |  |  |
| 25 | Renovating the drainage system on Phan Van Tri street (from Nguyen Van Cu street to the end of the street) | District 5 | Degraded culverts | - Length = 265 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 7,442 | 7,442 |  |  |  |  |  |
| 26 | Renovating the drainage system on Le Quang Sung street (from Trang Tu street to Nguyen Thi Nho street) | District 5 | Culvert D600 | - Length = 360 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 12,265 | 2,453 | 9,812 |  |  |  |  |
| 27 | Renovating the drainage system on Tan Hung street ( from Luong Nhu Hoc street to Truong Tu Giang street ) | District 5 | Degraded culverts | - Length = 300 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 8,891 | 8,891 |  |  |  |  |  |
| 28 | Renovating the drainage system on Tran Hung Dao street ( from Chau Van Liem street to Hoc Lac street) | District 5 | Culvert D400 | - Length = 490 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 16,671 |  | 3,334 | 13,337 |  |  |  |
| 29 | Renovating the drainage system on Tan Thanh street ( from Nguyen Thi Nho street to Thuan Kieu street) | District 5 | Degraded culverts | - Length = 820 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 22,979 |  | 4,596 | 18,383 |  |  |  |
| 30 | Renovating the drainage system on Trang Tu street (from Do Ngoc Thach street to Nguyen Thi Nho street) | District 5 | Culvert D400 | - Length = 630 meters - Installing culverts D1000-D1500 - Backfilling trench and re-asphalting pavements | 23,788 |  | 4,758 | 19,030 |  |  |  |
| 31 | Renovating the drainage system on Phung Hung street ( from Hong Bang street to Hai Thuong Lang Ong street) | District 5 | Culvert D400 | - Length = 390 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 10,930 |  | 2,186 | 8,744 |  |  |  |
| 32 | Renovating the drainage system on Hai Thuong Lang Ong street ( from Do Ngoc Thach street to Chau Van Liem street) | District 5 | Culverts D400, D600 | - Length = 360 meters - Installing 02 culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 20,500 |  | 4,100 | 16,400 |  |  |  |
| 33 | Renovating the drainage system on Le Lai street ( from Nguyen Trai street to Phan Chu Trinh street) | District 5 | Culverts D1000, D1200 | - Length = 2100 meters - Installing box culverts 2x[1,5x1,5]meters - Backfilling trench and re-asphalting pavements | 189,653 |  |  | 18,965 | 56,896 | 113,792 |  |
| 34 | Renovating the drainage system on Pham Huu Chi street ( from Vo Truong Toan street to Thuan Kieu street) | District 5 | Degraded culverts | - Length = 720 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 21,240 |  |  | 4,248 | 16,992 |  |  |
| 35 | Renovating the drainage system on Le Quang Sung street ( from Minh Phung street to Lo Gom canal) | District 6 | Culvert D400 | - Length = 500 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 14,791 | 4,437 | 10,354 |  |  |  | Urgent |
| 36 | Renovating the drainage system on Le Quang Sung street ( from Mai Xuan Thuong street to Minh Phung street) | District 6 | Culverts D400, D600 | - Length = 580 meters - Installing culverts D1000-D1500 - Backfilling trench and re-asphalting pavements | 21,928 |  |  | 4,386 | 17,542 |  |  |
| 37 | Renovating the drainage system on Hoang Le Kha street ( from Hong Bang street to Lo Gom street) | District 6 | Degraded culverts | - Length = 300 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 10,269 |  |  | 2,054 | 8,215 |  |  |
| 38 | Renovating the drainage system on Hau Giang street, Thap Muoi street(from Ngo Nhan Tinh street to Minh Phung street) | District 6 | Culverts D500, D600, D700 in two sides of the streets | - Length = 1300 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 21,000 | 7,000 | 14,000 |  |  |  | Approved by the People’s Committee in the notification No. 708/TB- VP dated November 17, 2010 |
| 39 | Renovating the drainage system on Pham Dinh Ho street ( from Hong Bang street to Le Quang Sung street) | District 6 | Culvert D600 | - Length = 300 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 8,891 |  | 1,778 | 7,113 |  |  |  |
| 40 | Renovating the drainage system on Tan Hoa Dong street ( from An Duong Vuong street to Phu Lam roundabout) | District 6 | Culvert D400, D800 | - Length = 1400 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 41,300 |  |  | 8,260 | 33,040 |  |  |
| 41 | Renovating the drainage system on Vinh Vien street ( from Ngo Gia Tu street to Nguyen Tri Phuong street) | District 10 | culverts D500 | - Length = 500 meters - Installing culvert D800-Blackfilling trench and re-asphalting pavements | 14,026 | 4,208 | 9,818 |  |  |  | Urgent |
| 42 | Renovating the drainage system on Vinh Vien street (from Ngo Quyen street to Ly Thuong Kiet street) | District 10 | Culvert D600 | - Length = 650 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 18,166 | 3,633 | 14,533 |  |  |  |  |
| 43 | Renovating the drainage system on Nguyen Chi Thanh street (from Hung Vuong street to Su Van Hanh street) | District 10 | culverts D600 | - Length = 200 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 5,595 | 1,679 | 3,917 |  |  |  | Urgent |
| 44 | Renovating the drainage system on Nguyen Chi Thanh street (from Ngo Quyen street to Ly Thuong Kiet street) | District 10 | Culverts [0,8x1,4]meters | - Length = 450 meters - Installing culverts D1500 - Backfilling trench and re-asphalting pavements | 19,957 | 5,987 | 13,970 |  |  |  | Urgent |
| 45 | Renovating the drainage system on Nguyen Chi Thanh street (from Su Van Hanh street to Ngo Quyen street) | District 10 | Culvert D600 | - Length = 900 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 25,217 |  | 5,043 | 20,174 |  |  |  |
| 46 | Renovating the drainage system on Ly Thuong Kiet street ( from 3 Thang 2 street to Tan Phuoc street) | District 10 | Culverts [0,8x1,4]meters | - Length = 350 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 11,948 | 3,584 | 8,364 |  |  |  | Urgent |
| 47 | Renovating the drainage system on Ngo Gia Tu street ( from the roundabout to Nguyen Tri Phuong street) | District 10 | Degraded culverts | - Length = 1150 meters - Installing culverts D1000-D1200 in two sides of the street - Backfilling trench and re-asphalting pavements | 78,409 |  |  | 15,682 | 62,727 |  |  |
| 48 | Renovating the drainage system on Ly Thuong Kiet street ( from Tan Phuoc street to Hung Vuong street) | District 10 | Arch culverts [0.8mx1.4m]meters | - Length = 700 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 23,897 |  |  | 4,779 | 19,118 |  |  |
| 49 | Renovating the drainage system on Hoa Hao street ( from Tran Nhan Ton street to Nguyen Tri Phuong street) | District 10 | culverts D600 | - Length = 700 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 23,897 | 7,169 | 16,728 |  |  |  | Urgent |
| 50 | Renovating the drainage system on Hoa Hao street ( from Nguyen Tri Phuong street to Ngo Quyen street) | District 10 | Culvert D600 | - Length = 400 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 13,628 |  | 2,726 | 10,902 |  |  |  |
| 51 | Renovating the drainage system on Hoa Hao street ( from Ly Thuong Kiet street to Le Dai Hanh street) | District 10 | Culvert D600 | - Length = 250 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 8,494 |  |  |  | 1,699 | 6,795 |  |
| 52 | Renovating the drainage system on Dong Nai street ( from To Hien Thanh street to Bac Hai street) | District 10 | Culverts D400, D800 | - Length = 800 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 23,600 |  | 4,720 | 18,880 |  |  |  |
| 53 | Renovating the drainage system on Nhat Tao street (from Nguyen Duy Duong street to Ngo Quyen street) | District 11 | culverts D600 | - Length = 630 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 17,644 | 5,293 | 12,351 |  |  |  | Urgent |
| 54 | Renovating the drainage system on Thai Phien street (from 3 Thang 2 street to Hung Vuong street) | District 11 | Degraded culverts | - Length = 200 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 5,595 | 5,595 |  |  |  |  |  |
| 55 | Renovating the drainage system on Han Hai Nguyen street (from Minh Phung street to 3 Thang 2 street) | District 11 | Culvert D600 | - Length = 600 meters - Installing culverts D1000-D1500 - Backfilling trench and re-asphalting pavements | 22,631 | 4,526 | 18,105 |  |  |  |  |
| 56 | Renovating the drainage system on 3 Thang 2 street (from Han Hai Nguyen street to Le Dai Hanh street) | District 11 | Degraded culverts | - Length = 1000 meters - Installing culverts D1200-D1500 - Backfilling trench and re-asphalting pavements | 40,765 |  | 8,153 | 32,612 |  |  |  |
| 57 | Renovating the drainage system on Ba Hat (from Nguyen Kim street to Ngo Gia Tu street) | District 11 | Culvert D400, D500 | - Length = 1400 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 41,300 |  | 8,260 | 33,040 |  |  |  |
| 58 | Renovating the drainage system on Phu Tho street (from Lac Long Quan street Hong Bang street) | District 11 | Culverts D400, D800 | - Length = 500 meters - Installing culverts D1200 - Backfilling trench and re-asphalting pavements | 18,610 |  | 3,722 | 14,888 |  |  |  |
| 59 | Renovating the drainage system on Do Tan Phong street (from Hoang Van Thu Street to Chien Thang street) | Phu Nhuan district | Dilapidated culverts | - Length = 650 meters - Installing culverts D600-D800 - Backfilling trench and re-asphalting pavements | 9,493 | 1,899 | 7,594 |  |  |  |  |
| 60 | Renovating the drainage system on Bui Dinh Tuy street (from alley 304 to Bui Dinh Tuy bridge ) | Binh Thanh district | Culverts D600, D800 | - Length = 1000 meters - Building drainage system and asphalt concrete pavement | 55,000 | 20,000 | 35,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 61 | Renovating the drainage system on Chu Van An Street (from Binh Hoa roundabout to Chu Van An bridge) | Binh Thanh district | Culverts D600, D800 | - Length = 1000 meters - Building drainage system in two sidewalks, expand the street with the limit of 25m, constructing asphalt concrete pavement | 95,000 | 0,200 | 28,440 | 66,360 |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 62 | Renovating the drainage system on Nguyen Xi Street (from Dinh Bo Linh street to Red Bridge) | Binh Thanh district | Degraded culverts D800 | - Length = 600 meters - Installing culverts D1000 - Backfilling trench and re-asphalting pavements | 18,614 | 3,723 | 14,891 |  |  |  |  |
| 63 | Renovating the drainage system on Lam Son street (from Phan Dang Luu Street to Nguyen Van Dau street) | Binh Thanh district | Dilapidated, small culverts | - Length = 450 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 13,254 |  | 2,651 | 10,603 |  |  |  |
| 64 | Renovating the drainage system on Nguyen Huy Tuong street (from Phan Dang Luu street to the end of the street) | Binh Thanh district | Dilapidated, small culverts | - Length = 150 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 4,446 |  | 0,889 | 3,557 |  |  |  |
| 65 | Renovating the drainage system on No Trang Long street( from Phan Dang Luu street to Le Quang Dinh street) | Binh Thanh district | Dilapidated culverts | - Length = 650 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 21,133 |  |  | 4,227 | 16,906 |  |  |
| 66 | Renovating the drainage system on An Duong Vuong street ( from Ba Hom street to Mui Tau street) | Binh Tan district | Culverts D600, D1000 | - Length = 1120 meters - Installing culverts D1500-D2000 - Backfilling trench and re-asphalting pavements | 60,494 |  |  |  | 12,099 | 48,395 |  |
| 67 | Renovating the drainage system on Kinh Duong Vuong street ( from Ong Buong bridge to Mui tau Phu Lam ) | Binh Tan district | Culverts D800, D1000, D1200 | - Length = 1800 meters - Installing culverts D1200-D1500 in the two sidewalks of the street - Backfilling trench and re-asphalting pavements | 141,835 |  |  | 14,184 | 42,551 | 85,101 |  |
| 68 | Renovating the drainage system on Hau Giang street ( from Thang Long street to house No. 17) | Tan Binh district | Dilapidated, small culverts | - Length = 150 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 4,446 | 4,446 |  |  |  |  |  |
| 69 | Renovating the drainage system on Nguyen Hong Dao street ( from Truong Chinh street to Au Co street) | Tan Binh district | Culverts D400, D800 | - Length = 1100 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 37,525 |  | 7,505 | 30,020 |  |  |  |
| 70 | Renovating the drainage system on Pham Phu Thu street ( from Lac Long Quan street to Dong Den street) | Tan Binh district | Culverts D400, D600 | - Length = 950 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 32,391 |  |  | 6,478 | 25,913 |  |  |
| 71 | Renovating the drainage system on Ba Van street ( from Nguyen Hong Dao street to Au Co street) | Tan Binh district | Culverts D400, D800 | - Length = 600 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 20,442 |  |  | 4,088 | 16,354 |  |  |
| 72 | Renovating the drainage system on Truong Cong Dinh street ( from Truong Chinh street to Au Co street) | Tan Binh district | Culverts D400, D800 | - Length = 850 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 28,936 |  |  |  | 5,787 | 23,149 |  |
| 73 | Renovating the drainage system on Dong Den street ( from Truong Chinh street to Bau Cat street) | Tan Binh district | Culverts D400, D800 | - Length = 600 meters - Installing culverts D1000 - Backfilling trench and re-asphalting pavements | 18,614 |  |  |  | 3,723 | 14,891 |  |
| Total length = 51225 meters |  |  |  |  | 2046,190 | 167,480 | 508,684 | 548,945 | 396,752 | 424,330 |  |
| 1 | Renovating the drainage system on Dang Nguyen Can street (from Tan Hoa Dong street to Tre bridge) | District 6 | Culverts D1200 | - Length = 300 meters - Installing box culvert [2x2]m (connected to DATP No. 3) - Backfilling trench and re-asphalting pavements | 23,442 |  | 4,688 | 18,754 |  |  |  |
| 2 | Renovating the drainage system on street No.26 ( from An Duong Vuong street to Lo Gom canal) | District 6 | Culverts D400, D1200 | - Length = 1200 meters - Installing box culvert [2mx2m] -Backfilling trench and re-asphalting pavements | 108,784 |  |  | 10,878 | 32,635 | 65,270 |  |
| 3 | Renovating the drainage system on Ly Chieu Hoang street (from An Duong Vuong street to Nguyen Van Luong street) | District 6 | culverts D800, D1000 ( two sides) | - Length = 1300 meters - Installing culverts D1000, D1200 - Backfilling trench and re-asphalting pavements | 44,339 |  |  | 8,868 | 35,471 |  |  |
| 4 | Renovating the drainage system on Binh Phu street (from Hau Giang street to Ly Chieu Hoang street) | District 6 | Culverts D400, D1200 | - Length = 1200 meters - Installing culverts D1200-D1800 - Backfilling trench and re-asphalting pavements | 54,160 |  |  | 10,832 | 43,328 |  |  |
| 5 | Renovating the drainage system on Cho Lon street (from Nguyen Van Luong street to Binh Phu street) | District 6 | Degraded culverts | - Length = 500 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 17,083 |  |  |  | 3,417 | 13,666 |  |
| 6 | Renovating the drainage system on Su Van Hanh street ) from 3 Thang 2 street to To Hien Thanh street) | District 10 | Culverts D400, D800 | - Length = 1200 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 39,057 |  |  |  | 7,811 | 31,246 |  |
| 7 | Renovating the drainage system on Bau Cat street( from Truong Cong Dinh street to Vo Thanh Trang street) | Tan Binh district | Culverts D400, D1000 | - Length = 1000 meters - Installing box culverts [1.6mx1.6m] - Backfilling trench and re-asphalting pavements | 51,365 |  |  | 10,273 | 41,092 |  |  |
| Total length = 06700 meters |  |  |  |  | 338,230 | 0,000 | 4,688 | 59,605 | 163,754 | 110,182 |  |
| Total length = 57925 meters |  |  |  |  | 2384,420 | 167,480 | 513,372 | 608,549 | 560,506 | 534,512 |  |
| 1 | Renovating the drainage system on Truong Vinh Ky street (from Tan Son Nhi street to Nguyen Xuan Khoat street) | Tan Phu street | Culvert D800 | - Length = 580 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 18,922 | 3,784 | 15,138 |  |  |  |  |
| 2 | Renovating the drainage system on Go Dau street (from Tan Ky - Tan Quy street to Tan Son Nhi street) | Tan Phu street | Culvert D600 | - Length = 2080 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 67,698 | 6,770 | 20,309 | 40,619 |  |  |  |
| 3 | Renovating the drainage system on Tan Huong street ( from Binh Long street to Doc Lap street) | Tan Phu street | Culvert D800 | - Length = 1680 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 54,679 |  | 10,936 | 43,743 |  |  |  |
| 4 | Renovating the drainage system in area restricted by Tan Ky Tan Quy street, Binh Long street, Tan Huong street, Doc Lap street, Tan Son Nhi street, Tran Van On street | Tan Phu street | Culverts D600, D800 | - Length = 2800 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 91,132 |  |  |  | 18,226 | 72,906 |  |
| 5 | Renovating the drainage system on Ho Ngoc Lam street ( from National Route 1A to Ben Phu Dinh street) | Binh Tan district | Small culverts, low street | - Length = 3500 meters - Installing culverts D800-D1500 - Backfilling trench and re-asphalting pavements | 126,730 |  |  | 12,673 | 38,019 | 76,038 |  |
| Total length = 10640 meters |  |  |  |  | 359,161 | 10,554 | 46,383 | 97,035 | 56,245 | 148,944 |  |
| 1 | Renovating the drainage system on Kinh Duong Vuong street (from Mui tau Phu Lam to An Lac roundabout) | Binh Tan district | Culverts D800, D1000, D1200 | - Length = 3500 meters -Installing culverts D1200-D1500 in the two sidewalks of the street - Backfilling trench and re-asphalting pavements | 275,846 |  |  | 27,585 | 82,754 | 165,508 |  |
| Total length = 03500 meters |  |  |  |  | 275,846 | 0,000 | 0,000 | 27,585 | 82,754 | 165,508 |  |
| Total length = 14140 meters |  |  |  |  | 635,007 | 10,554 | 46,383 | 124,620 | 138,999 | 314,451 |  |
| 1 | Renovating the drainage system on Nguyen Van Nghi street (from Nguyen Kiem street to Hang bridge) | Go Vap street | Small and degraded culverts | - Length = 1500 meters - Installing culverts D1000-D1200 - Backfilling trench and re-asphalting pavements | 57,000 | 10,000 | 47,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 2 | Renovating Tan Tru canal ( from Pham Van Bach street to Hy Vong canal) | Tan Binh street | - B=2-4m. - The canal has a lot of garbage, mud, black water and bad smell - Many canal sections are replaced with culverts. | - Length = 1200 meters - Installing box culverts, constructing road on the box culverts - Dredging, widening, and constructing embankments in order to prevent trespass | 162,000 | 0,500 | 0,000 | 0,000 | 53,833 | 107,667 | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 3 | Renovating the drainage system in the culverts across Tan Xuan street, Xuan Thoi Dong street | Hoc Mon district | degraded and small culverts | - Length = 200 meters - Installing culvert D800 - Installing culvert D1200 along the National Route 22 | 6,509 | 6,509 |  |  |  |  |  |
| 4 | Renovating the drainage system on To Ky street ( from Hoc Mon canal to Nguyen Anh Thu street) | Hoc Mon district | Culverts D600, D800, combined with ditch | - Length = 500 meters - Installing culverts D600-D1000 - Backfilling trench and re-asphalting pavements | 14,337 |  | 2,867 | 11,470 |  |  |  |
| 5 | Renovating the drainage system on Tran Van Muoi street( from Lien Xa street to National Route 22) | Hoc Mon district | Asphalt concrete road with the width of 6-7m, sidewalk's width of 1-2m, no drainage system | - Length = 2200 meters - Installing culverts D800-D1500 - Backfilling trench and re-asphalting pavements | 59,556 |  |  |  | 11,911 | 47,645 |  |
| 6 | Renovating the drainage system on Lien Xa street (from Nguyen Thi Soc street to Tran Van Muoi street) | Hoc Mon district | Asphalt concrete road with the width of 6-7m, no drainage system | - Length = 1600 meters - Installing culverts D800-D1200 - Backfilling trench and re-asphalting pavements | 52,075 |  |  |  | 10,415 | 41,660 |  |
| Total length = 7200 meters |  |  |  |  | 351,48 | 17,01 | 49,87 | 11,47 | 76,16 | 196,97 |  |
| 1 | Renovating the drainage system on Nguyen Anh Thu street ( from To Ky street to National Route 22) | Hoc Mon district-district 12 | 2 culverts D600 | - Length = 1700 meters - Installing culverts D1000-D1500 - Backfilling trench and re-asphalting pavements | 64,17 |  |  |  | 12,83 | 51,34 |  |
| Total length = 1700 meters |  |  |  |  | 64,172 | 0,000 | 0,000 | 0,000 | 12,834 | 51,338 |  |
| Total length = 8900 meters |  |  |  |  | 415,649 | 17,009 | 49,867 | 11,470 | 88,994 | 248,309 |  |
| 1 | Renovating the drainage system on Le Van Thinh street and street No.22 ( from Nguyen Thi Dinh street to Nguyen Duy Trinh street) | District 2 | Culvert D800 and catch pits two sides of the street | - Length = 1700 meters - Installing culverts D800-D1000 - Backfilling trench and re-asphalting pavements | 50,191 |  |  |  | 10,038 | 40,153 |  |
| 2 | Renovating the drainage system on Thao Dien-Quoc Huong-Xuan Thuy-Nguyen Van Huong ( Thao Dien residential area) | District 2 | Culvert D800 and catch pits two sides of the street | - Length = 6500 meters - Installing culverts D1000-D1500 - Backfilling trench and re-asphalting pavements | 245,219 |  |  | 24,522 | 73,566 | 147,131 |  |
| Total length = 8200 meters |  |  |  |  | 295,410 | 0,000 | 0,000 | 24,522 | 83,604 | 187,284 |  |
| 1 | Renovating the drainage system on Luong Dinh Cua street ( from Tran Nao street to Thu Thiem ferry) | District 2 | Degraded culverts | - Length = 2500 meters - Installing culverts D1000-D2000 - Backfilling trench and re-asphalting pavements | 118,355 |  |  | 23,671 | 94,684 |  |  |
| 2 | Renovating the drainage system on Nguyen Thi Dinh street ( from Luong Dinh Cua to street No.25B) | District 2 | Culvert D800 and catch pits two sides of the street | - Length = 4000 meters - Installing culverts D1200-D2000 - Backfilling trench and re-asphalting pavements | 201,460 |  |  | 40,292 | 161,168 |  |  |
| Total length = 6500 meters |  |  |  |  | 319,815 | 0,000 | 0,000 | 63,963 | 255,852 | 0,000 |  |
| Total length = 14700 meters |  |  |  |  | 615,225 | 0,000 | 0,000 | 88,485 | 339,456 | 187,284 |  |
| 1 | Renovating the drainage system on Kha Van Can street ( from Vo Van Ngan street to Ngang bridge) | Thu Duc district | Box culvert is installed but the drainage direction impedes the drainage flow, causing erosion to households around Ngang bridge | - Length = 1000 meters - Installing more culverts D1200- D1500 in lower section of ngang bridge - Backfilling trench and re-asphalting pavements | 4,018 | 0,804 | 3,214 |  |  |  |  |
| Total length = 100 meters |  |  |  |  | 4,018 | 0,804 | 3,214 | 0,000 | 0,000 | 0,000 |  |
| 1 | Renovating the drainage system on Nguyen Quyen street (from Tung Thien Vuong street to Ben Binh Dong street) | District 8 | culverts D300 | - Length = 400 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 10,977 | 3,293 | 7,684 |  |  |  | Urgent |
| 2 | Renovating the drainage system on Luong Ngoc Quyen street (from Tung Thien Vuong street to Ben Binh Dong street) | District 8 | culverts D400 | - Length = 220 meters - Installing culverts D600, D800 - Backfilling trench and re-asphalting pavements | 5,992 | 1,198 | 4,794 |  |  |  |  |
| 3 | Renovating the drainage system on Nguyen Che Nghia street (from Nguyen Duy street to Ben Binh Dong street) | District 8 | culverts D600, D800 | - Length = 400 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 11,800 | 2,360 | 9,440 |  |  |  |  |
| 4 | Renovating the drainage system on Tran Nguyen Han street (from Ben Binh Dong street to Tung Thien Vuong street) | District 8 | culverts D600 | - Length = 220 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 6,193 | 1,239 | 4,954 |  |  |  |  |
| 5 | Renovating the drainage system on Vinh Nam street (from Tung Thien Vuong street to Ben Binh Dong street) | District 8 | culverts D600, D800 | - Length = 170 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 4,737 | 0,947 | 3,790 |  |  |  |  |
| 6 | Renovating the drainage system on Nguyen Thi Tan street ( from Da Nam street to Ta Quang Buu street) | District 8 | culverts D600 | - Length = 1100 meters - Installing culverts D800, D1200 - Backfilling trench and re-asphalting pavements | 16,318 |  |  | 3,264 | 13,054 |  |  |
| 7 | Renovating the drainage system on Hung Phu street ( from Chu Y bridge to Chanh Hung street) | District 8 | Culverts D500, D400, D600 | - Length = 1750 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 51,645 |  |  | 10,329 | 41,316 |  |  |
| 8 | Renovating the drainage system on Hung Phu street ( from Chanh Hung street to Xom Cui street) | District 8 | culverts D400, D600, | - Length = 950 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 28,045 |  |  |  | 5,609 | 22,436 |  |
| 9 | Renovating the drainage system on Pham The Hien ( from Ba Tang bridge to Nhi Thien Duong bridge) | District 8 | culverts D400, D800, | - Length = 2100 meters - Installing culverts D800, D1500 - Backfilling trench and re-asphalting pavements | 76,057 |  |  |  | 15,211 | 60,846 |  |
| 10 | Renovating the drainage system on Pham The Hien ( from Ba Tang bridge to Ba To street) | District 8 | culverts D400, D800, | - Length = 3500 meters - Installing culverts D800, D1500 - Backfilling trench and re-asphalting pavements | 118,237 |  |  | 11,824 | 35,471 | 70,942 |  |
| 11 | Renovating the drainage system on Ben Phu Dinh street ( from Ho Ngoc Lam street to Phu Dinh bridge) | District 8 | culverts D400, D600, | - Length = 3500 meters - Installing culverts D800, D1500 - Backfilling trench and re-asphalting pavements | 118,237 |  |  | 11,824 | 35,471 | 70,942 |  |
| 12 | Renovating the drainage system on Xom Cui street ( from Ba Dinh street to Ben Binh Dong street) | District 8 | culverts D600, D800, | - Length = 500 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 14,791 |  |  |  | 2,958 | 11,833 |  |
| 13 | Renovating the drainage system on Huynh Tan Phat street ( Tan Thuan bridge to Phu Xuan street) | District 7 | culverts D800, D1000 | - Length = 4000 meters - Installing box culvert 2x[1,5x1,5]meters - Backfilling trench and re-asphalting pavements | 361,161 |  |  | 36,116 | 108,348 | 216,697 |  |
| Total length = 18210 meters |  |  |  |  | 824,190 | 9,038 | 30,662 | 73,356 | 257,440 | 453,695 |  |
| Total length = 113975 meters |  |  |  |  | 4878,509 | 204,884 | 643,498 | 906,480 | 1385,395 | 1738,252 |  |
| 1 | Building the drainage system on Tam Vu street ( from Xo Viet Nghe Tinh street to Xuyen Tam canal) | Binh Thanh district | The drainage system has not been installed | - Length = 800 meters - Installing culverts D1500, D1800 - Backfilling trench and re-asphalting pavements | 42,520 | 8,504 | 34,016 |  |  |  |  |
| 2 | Building the drainage system on alley 10- Mien Dong bus station alley ( from Xo Viet Nghe Tinh street to Xuyen Tam canal) | Binh Thanh district | The drainage system has not been installed | - Length = 700 meters - Installing culverts D1500, D1800 - Backfilling trench and re-asphalting pavements | 52,000 | 5,200 | 15,600 | 31,200 |  |  |  |
| 3 | Building the drainage system at alley 618/1-alley 618/8 ( Xo Viet Nghe Tinh street); Alley 79B (Nguyen Xi street) | Binh Thanh district | The drainage system has not been installed | - Length = 650 meters - Installing culverts D600, D1200 - Backfilling trench and re-asphalting pavements | 19,173 |  | 3,835 | 15,338 |  |  |  |
| 4 | Building the drainage system on street No.14( from Le Van Quoi street to Nuoc Den canal) | Binh Tan district | The drainage system has not been installed | - Length = 1400 meters - Installing 750 meters of box culvert [2.0x1.6]meters ( the remaining part) - Backfilling trench and re-asphalting pavements | 46,822 | 9,364 | 37,458 |  |  |  |  |
| 5 | Building the drainage system on An Duong Vuong street ( from Ly Chieu Hoang street to My Thuan bridge) | Binh Tan district | The drainage system has not been installed | - Length = 680 meters - Installing box culvert [2.5x2.5] meters - Backfilling trench and re-asphalting pavements | 82,887 | 16,577 | 66,310 |  |  |  |  |
| Total length = 3580 meters |  |  |  |  | 243,402 | 39,646 | 157,218 | 46,538 | 0,000 | 0,000 |  |
| 1 | Building the drainage system on Tran Dai Nghia street ( from National Route 1A to Cai Trung bridge) | Binh Tan-Binh Chanh districts | The drainage system has not been installed | - Length = 2000 meters - Installing culverts D1200-D2000 - Backfilling trench and re-asphalting pavements | 200,000 | 0,500 | 39,900 | 159,600 |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 2 | Building the drainage system on Tran Dai Nghia street ( from Le Ngung street to Cai Trung bridge) | Binh Tan-Binh Chanh districts | The drainage system has not been installed | - Length = 1300 meters - Installing culverts D1200-D2000 - Backfilling trench and re-asphalting pavements | 126,847 | 1,000 |  | 25,169 | 50,339 | 50,339 |  |
| 3 | Building the drainage system on Trinh Quang Nghi street ) from Phong Phu street to National Route 50) | Binh Chanh district | The drainage system has not been installed | - Length = 200 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 5,900 | 5,900 |  |  |  |  |  |
| 4 | Building the drainage system on National Route 1A ( from Dong Tay highway to Binh Dien bridge) | Binh Chanh district | Drainage ditch | - Length = 1000 meters - Installing culverts D1200-D1500 in the two sides of the street - Backfilling trench and re-asphalting pavements | 78,797 |  | 15,759 | 63,038 |  |  |  |
| 5 | Building the drainage system on Trinh Quang Nghi street ( from Nguyen Van Linh street to National Route 50) | Bin Chan district | The drainage system has not been installed | - Length = 2300 meters - Installing culverts D800, D1500 - Backfilling trench and re-asphalting pavements | 83,296 |  |  | 8,330 | 24,989 | 49,978 |  |
| 6 | Building the drainage system on An Duong Vuong street ( from My Thuan bridge to Ben Phu Dinh street) | Binh Tan district | The drainage system has not been installed | - Length = 2800 meters - Installing culverts D800-, D1500 - Backfilling trench and re-asphalting pavements | 94,590 |  |  | 9,459 | 28,377 | 56,754 |  |
| Total length = 9600 meters |  |  |  |  | 589,430 | 7,400 | 55,659 | 265,596 | 103,705 | 157,070 |  |
| 1 | Building the drainage system on National Route 1A (from Le Thi Rieng street to Nguyen Van Qua street) | District 12 | The drainage system has not been installed | - Length = 1600 meters - Installing 2 culverts D1000 - Backfilling trench and re-asphalting pavements | 108,000 | 20,000 | 88,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 2 | Building the drainage system on National Route 1A ( from An Suong overpass to Nguyen Van Qua street) | District 12 | Drainage ditch | - Length = 1400 meters - Installing culverts D1000, D1200 - Backfilling trench and re-asphalting pavements | 95,397 |  |  | 9,540 | 28,619 | 57,238 |  |
| 3 | Building the drainage system on National Route 1A (from Le Thi Rieng street to Ga intersection ) | District 12 | Drainage ditch | - Length = 2900 meters - Installing culverts D1000, D1200 - Backfilling trench and re-asphalting pavements | 197,703 |  |  | 19,770 | 59,311 | 118,622 |  |
| 4 | Building the drainage system on National Route 1A (from Binh Phuoc overpass to Ga intersection) | District 12 | Drainage ditch | - Length = 3500 meters - Installing culverts D1000, D1200 - Backfilling trench and re-asphalting pavements | 238,588 |  |  | 23,859 | 71,576 | 143,153 |  |
| 5 | Building the drainage system on Le Lai street (the whole street) | Go Vap district | The drainage system has not been installed | - Length = 400 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 11,191 | 11,191 |  |  |  |  |  |
| 6 | Building the drainage system on Le Loi street ( from Nguyen Van Bao street to Le Lai street) | Go Vap district | The drainage system has not been installed | - Length = 4600 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 9,600 | 9,600 |  |  |  |  |  |
| 7 | Building the drainage system on Tran Quoc Tuan street ( from Le Quang Dinh street to Phan Van Tri street) | Go Vap district | The drainage system has not been installed | - Length = 600 meters - Installing culverts D600, D800 - Backfilling trench and re-asphalting pavements | 20,000 | 15,000 | 5,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 8 | Building the drainage system on Le Loi street ( from Le Lai street to Nguyen Kiem street) | Go Vap district | The drainage system has not been installed | - Length = 1050 meters - Installing culverts D600, D1000 - Backfilling trench and re-asphalting pavements | 30,004 |  |  | 6,001 | 24,003 |  |  |
| 9 | Building the drainage system on National Route 22 (Nuoc Nhi drain to Dinh Bau Tre street) | Cu Chi district | The drainage system has not been installed | - Length = 1200 meters - Installing culverts D1000, D1500 - Backfilling trench and re-asphalting pavements | 28,000 | 10,000 | 18,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 10 | Building the drainage system on Provincial Route 8 ( from National Route 22 to Lang The bridge) | Cu Chi district | The drainage system has not been installed | - Length = 6500 meters - Installing culverts D1000-box culvert [2x2]meters - Backfilling trench and re-asphalting pavements | 354,404 |  |  | 35,440 | 106,321 | 212,642 |  |
| 11 | Building the drainage system on Provincial Route 8 ( from Lang The bridge Provincial Route 15) | Cu Chi district | The drainage system has not been installed | - Length = 4700 meters - Installing culverts D1000-box culvert [2x2]meters - Backfilling trench and re-asphalting pavements | 256,273 |  |  | 25,627 | 76,882 | 153,764 |  |
| 12 | Building the drainage system on Provincial Route 15 ( from Provincial Route 8 to Ben Nay bridge) | Cu Chi district | Drainage ditch | - Length = 3700 meters - Installing culverts D1000, D2000 - Backfilling trench and re-asphalting pavements | 175,136 |  |  |  | 35,027 | 140,109 |  |
| 13 | Building the drainage system on Provincial Route 15 (from Phu Thuan street to Thai Thai bridge) | Cu Chi district | Drainage ditch | - Length = 900 meters - Installing culverts D800, D1200 -Backfilling trench and re-asphalting pavements | 29,337 |  |  |  | 5,867 | 23,470 |  |
| 14 | Building the drainage system on Phan Van Hon (from Tran Van Muoi to People’s Committee of Thoi Dong commune | Hoc Mon district | The drainage system has not been installed | - Length = 1000 meters - Installing culverts D800 - Backfilling trench and re-asphalting pavements | 27,977 |  |  | 5,595 | 22,382 |  |  |
| Total length = 31510 meters |  |  |  |  | 1581,610 | 65,791 | 111,000 | 125,833 | 429,989 | 848,997 |  |
| 1 | Building a drainage system on Luong Dinh Cua street ( from Tran Nao street to Nguyen Thi Dinh street) | District 2 | The drainage system has not been installed | - Length = 2700 meters - Installing culverts D1200, D2000 - Backfilling trench and re-asphalting pavements | 136,049 |  |  | 13,605 | 40,815 | 81,629 |  |
| 2 | Renovating the drainage system on Nguyen Thi Dinh street (from street 25B to Cat Lai ferry station) | District 2 | The drainage system has not been installed | - Length = 1700 meters - Installing culverts D1200, D2000 - Backfilling trench and re-asphalting pavements | 85,684 |  |  |  | 17,137 | 68,547 |  |
| 3 | Renovating the drainage system on Nguyen Duy Trinh (from Gong Ong To market to Xay Dung bridge) | District 2 | Drainage ditch | - Length = 3600 meters - Installing culverts D800-D2000, box culvert - Backfilling trench and re-asphalting pavements | 164,860 |  |  | 16,486 | 49,458 | 98,916 |  |
| 4 | Building a drainage system along the underpass of Saigon bridge ( from Quoc Huong street to Tran Nao street) | District 2 | The drainage system has not been installed | - Length = 900 meters - Installing culverts D600 - Backfilling trench and re-asphalting pavements | 23,584 |  |  |  | 4,717 | 18,867 |  |
| 5 | Building a drainage system on Nguyen Van Tang street( from Le Van Viet street to Nguyen Xien street) | District 9 | The drainage system has not been installed | - Length = 2200 meters - Installing culverts D1000, D2000 - Backfilling trench and re-asphalting pavements | 104,099 |  | 10,410 | 31,230 | 62,459 |  |  |
| 6 | Building a drainage system on Tang Nhon Phu street (from Do Xuan Hop street to Dinh Phong Phu street) | District 9 | The drainage system has not been installed | - Length = 2000 meters - Installing culverts D1000, D2000 - Backfilling trench and re-asphalting pavements | 94,635 |  |  | 9,464 | 28,391 | 56,781 |  |
| 7 | Building a drainage system on Do Xuan Hop street (from Rach Chiec bridge to Nguyen Duy Trinh street) | District 9 | The drainage system has not been installed | - Length = 2400 meters - Installing culverts D1200, D2000 - Backfilling trench and re-asphalting pavements | 120,876 |  |  |  | 24,175 | 96,701 |  |
| 8 | Building a drainage system on Do Xuan Hop street (from Ha Noi Highway to Rach Chiec bridge) | District 9 | The drainage system has not been complete | - Length = 3200 meters - Installing culverts D1200, D2000 - Backfilling trench and re-asphalting pavements | 161,168 |  |  | 16,117 | 48,350 | 96,701 |  |
| 9 | Building a drainage system on La Xuan Oai street (from Le Van Viet street to Rach Go Dua bridge) | District 9 | The drainage system has not been installed | - Length = 2300 meters - Installing culverts D1000, D2000 - Backfilling trench and re-asphalting pavements | 108,891 |  |  |  | 21,778 | 87,113 |  |
| 10 | Building a drainage system on Le Van Viet street (from Ha Noi highway to Hoang Huu Nam street) | District 9 | The drainage system has not been complete | - Length = 4700 meters - Installing culverts D1200, D2000 - Backfilling trench and re-asphalting pavements | 236,779 |  |  | 23,678 | 71,034 | 142,067 |  |
| 11 | Building a drainage system on Lo Lu street (from La Xuan Oai street to Nguyen Xien street) | District 9 | The drainage system has not been installed | - Length = 2600 meters - Installing culverts D1000, D2000 - Backfilling trench and re-asphalting pavements | 123,026 |  |  | 12,303 | 36,908 | 73,816 |  |
| 12 | Renovating the drainage system on Nguyen Xien street ( from Nguyen Van Tang street to Long Thuan street) | District 9 | The drainage system has not been installed | - Length = 3500 meters - Installing culverts D1000, D2000 - Backfilling trench and re-asphalting pavements | 165,672 |  |  | 16,567 | 49,702 | 99,403 |  |
| Total length = 31800 meters |  |  |  |  | 1525,323 | 0,000 | 10,410 | 139,449 | 454,923 | 920,541 |  |
| 1 | Renovating the drainage system on Tam Binh street (from Hiep Binh street to To Ngoc Van street) | Thu Duc district | The drainage system has not been installed | - Length = 2800 meters - Installing culverts D1200 -D2000 - Backfilling trench and re-asphalting pavements | 112,000 | 20,000 | 92,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 2 | Renovating the drainage system on Binh Phu street ( the whole street) | Thu Duc district | The drainage system has not been installed | - Length = 1000 meters - Installing culverts D800, D1200 - Backfilling trench and re-asphalting pavements | 34,000 | 10,000 | 24,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 3 | Dredging Nuoc Trong canal (from Ngo Chi Quoc bridge to the T-junction of Cau Dat cannal and Binh Thuy canal) | Thu Duc district | The drainage system has not been installed | - Length = 1000 meters - Installing culverts D800, D1200 - Backfilling trench and re-asphalting pavements | 20,000 | 10,000 | 10,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 4 | Building a drainage system on Cay Keo street ( the whole street) | Thu Duc district | The drainage system has not been installed | - Length = 1400 meters - Installing culverts D800, D1200 - Backfilling trench and re-asphalting pavements | 40,000 | 10,000 | 30,000 |  |  |  | Approved in the Notification No. 708/TB- VP dated November 17, 2010 |
| 5 | Building a drainage system on street No.2 ( from Ha Noi Highway to street No.11) | Thu Duc district | The drainage system has not been installed | - Length = 1400 meters - Installing culverts D800, D1200 - Backfilling trench and re-asphalting pavements | 45,566 |  |  |  | 9,113 | 36,453 |  |
| Total length = 7600 meters |  |  |  |  | 251,566 | 50,000 | 156,000 | 0,000 | 9,113 | 36,453 |  |
| 1 | Building a drainage system on Hoang Quoc Viet street (from Huynh Tan Phat street to Dao Tri street) | District 7 | The drainage system has not been installed | - Length = 710 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 20,965 |  |  | 4,193 | 16,772 |  |  |
| 2 | Building a drainage system on Chuyen Dung 9 street (from Huynh Tan Phat street to the end of Chuyen Dung street) | District 7 | The drainage system has not been installed | - Length = 930 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 27,414 |  |  | 5,483 | 21,931 |  |  |
| 3 | Building a drainage system on Dao Tri street (from Hoang Quoc Viet street to Go O Moi street) | District 7 | The drainage system has not been installed | - Length = 1900 meters - Installing culverts D800, D1200 - Backfilling trench and re-asphalting pavements | 61,884 |  |  |  | 12,377 | 49,507 |  |
| 4 | Building a drainage system on Pham Huu Lau street ( from Huu Phuoc bridge to Le Van Luong street) | Nha Be district | The drainage system has not been installed | - Length = 3100 meters - Installing culverts D800, D1200 - Backfilling trench and re-asphalting pavements | 100,941 |  |  | 10,094 | 30,282 | 60,565 |  |
| 5 | Building a drainage system on Nguyen Binh street (from Huynh Tan Phat street to Muong Chuoi bridge) | Nha Be district | The drainage system has not been installed | - Length = 3000 meters - Installing culverts D1000-D2000, box culvert - Backfilling trench and re-asphalting pavements | 141,953 |  |  | 14,195 | 42,586 | 85,172 |  |
| 6 | Building a drainage system on Dao Su Tich street (from Le Van Luong street to Long An boundary) | Nha Be district | The drainage system has not been installed | - Length = 3400 meters - Installing culverts D800, D1000 - Backfilling trench and re-asphalting pavements | 100,299 |  |  |  | 20,060 | 80,239 |  |
| Total length = 13040 meters |  |  |  |  | 453,456 | 0,000 | 0,000 | 33,965 | 144,008 | 275,483 |  |
| Total length = 97130.000 meters |  |  |  |  | 4644,787 | 162,837 | 490,287 | 611,381 | 1141,738 | 2238,545 |  |
| Total length = 211105.000 meters |  |  |  |  | 9523,296 | 367,721 | 1133,786 | 1517,860 | 2527,133 | 3976,797 |  |

APPENDIX 2B

SYSTEM OF WASTEWATER COLLECTION AND WASTEWATER TREATMENT PLANTS (Enclosed herewith Decision No. 26/2011/QĐ-UBND dated May 14, 2011 of People’s Committee of Ho Chi Minh city)

| No. | Project’s name | Place | Size | Starting-completion time | Total investment | Capital requirement per year (million VND) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 |  |  |
| I | Loan |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total |  |  |  | 30.149.830 | 2.534.980 | 5.067.570 | 5.523.410 | 5.861.700 | 5.063.320 | 1.569.880 |  |  |
| 1 | Project of water environment Improvement of Ho Chi Minh City (1st period) | Ho Chi Minh city | - Dredging 7,3 km and constructing 6,3km of embankments - Renovating the rain water drainage system - Constructing 6594 m of main culvert and 7018m of branch culvert - Renovating existing 9637m of drain and 3km of conveying culvert - Building wastewater treatment plant with capacity of 141000m3/ day | 2004-2011 | 4.163.950 | 1.128.000 | 268.000 |  |  |  |  |  |  |
|  | Total |  |  |  | 4.163.950 | 1.128.000 | 268.000 |  |  |  |  |  |  |
| 2 | Project of water environment Improvement in Ben Nghe - Tau Hu – Kenh Doi- Kenh Te basin (2nd period); | Ho Chi Minh city | Renovating canal, installing pumping stations and box culverts, expanding wastewater treatment plants | 2010-2014 | 8.169.590 |  | 1.835.000 | 2.232.000 | 2.907.000 | 2.432.000 | 953.000 |  |  |
| 3 | Project of Environmental sanitation of Ho Chi Minh City (Nhieu Loc-Thi Nghe basin) of the first period | Ho Chi Minh city | - Building 9 km of culvert. - Building pumping stations with capacity of 64000 m3 / hour. - Renovating Nhieu Loc-Thi Nghe canal: dredging, constructing 16km embankments at two banks - Replacing, extending about 65 km of culverts levels 2 and 3 | 2001- 2010 | 3.695.060 | 576.360 |  |  |  |  |  |  |  |
|  | Total |  |  |  | 3.695.060 | 576.360 |  |  |  |  |  |  |  |
| 4 | Project of environmental Sanitation in Nhieu Loc - Thi Nghe basin (2nd period) | Ho Chi Minh city | building a system of wastewater collection culvert and wastewater treatment plant | 2010- 2014 | 400 million USD |  | 100 million USD | 100 million USD | 100 million USD | 100 million USD |  |  |  |
|  |  |  |  |  | 7.800.000 |  | 1.950.000 | 1.950.000 | 1.950.000 | 1.950.000 |  |  |  |
| 5 | Project of improvement of drainage system in Tan Hoa-Lo Gom basin | Ho Chi Minh city | - Renovating, installing 23,3 km of box culvert and culvert - Renovating Tan Hoa-Lo Gom canal | 2007-2015 | 6.321.230 | 830.620 | 1.014.570 | 1.341.410 | 1.004.700 | 681.320 | 616.880 |  |  |
|  | Total |  |  |  | 6.321.230 | 830.620 | 1.014.570 | 1.341.410 | 1.004.700 | 681.320 | 616.880 |  |  |
| II | Budget capital |  |  |  | 25.101.741 | 0 | 4.189.946 | 5.000.000 | 5.000.000 | 5.000.000 | 4.480.000 |  |  |
| 1 | Wastewater treatment station of Suoi Nhum canal |  | 65.000m /day Capacity of 365,00m/day | 2008- 2011 | 670.000 |  | 570.000 |  |  |  |  |  |  |
| 2 | draining and improve the pollution in Tham Luong - Ben Cat – Rach Nuoc Len canal (1st period) | Ho Chi Minh city | Dredging the canal with the length of 32, 735m, installing 133 culverts, repairing 16 old culverts and 5 traffic bridges | 2007- 2011 | 1.951.741 |  | 619.946 |  |  |  |  |  |  |
| 3 | draining and improve the pollution in Tham Luong - Ben Cat – Rach Nuoc Len canal (2nd period) | Ho Chi Minh city | Building the plant of Tham Luong - Ben Cat, West Saigon; rainwater and wastewater collection system, pumping station; Rach Nuoc Len culvert | 2010- 2015 | 22.480.000 |  | 3.000.000 | 5.000.000 | 5.000.000 | 5.000.000 | 4.480.000 |  |  |
| Total (I+II) |  |  |  |  | 55.251.571 | 2.534.980 | 9.257.516 | 10.523.410 | 10.861.700 | 10.063.320 | 6.049.880 |  |  |

Note: The exchange rate on December 12, 2010 is 1USD=19500 VND

APPENDIX 2C

PROJECTS UNDER THE PRIME MINISTER’S DECISION NO. 1547 (Enclosed herewith Decision No. 26/2011 / QD-UBND dated May 14, 2011 of the People's Committee of Ho Chi Minh city)

| No. | Project’s name | Location | Size | Starting-completion time | Total investment | capital requirement per year (billion VND) |  |  |  |  | Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2011 | 2012 | 2013 | 2014 | 2015 |  |
|  | Total |  |  |  | 14.664,579 | 3.311,985 | 3.004,741 | 2.795,839 | 2.800,000 | 4.122,000 |  |
| 1 | Nhieu Loc-Thi Nghe tide control culvert | District 1- Binh Thanh | Breadth B=58m, bottom level:-4m, Pumping station capacity: 48m3/s. | 2010 - 2012 | 292,000 | 250,000 | 4,344 |  |  |  | Application of the EPC |
| 2 | Kinh river tide control culvert | Nha Be district | Breadth B = 120m, bottom level : -5,5m | 2011- 2013 | 748,000 | 300,000 | 300,000 | 144,500 |  |  | Application of the EPC |
| 3 | Tan Thuan tide control culvert | Districts 4, 7 | Breadth B = 65m, bottom level : -6m | 2011- 2013 | 647,139 | 200,000 | 300,000 | 145,339 |  |  | Application of the EPC |
| 4 | Phu Xuan tide control culvert | Nha Be district | Breadth = 120m, bottom level : -5,5m | 2012 - 2014 | 822,000 | 1.500,000 | 150,000 | 370,000 | 300,000 |  | Application of the EPC |
| 5 | Ben Nghe tide control culvert | Districts 1, 4 | Breadth B = 20m, bottom level : -4m | 2012 - 2013 | 171,000 | 1,500 | 79,000 | 90,000 |  |  | Depending on the completion time of Thu Thiem Tunnel. Application of the EPC |
| 6 | Rach Tra tide control culvert | Cu Chi-Hoc Mon Districts | Breadth B = 60m, bottom level : -4m | 2013 - 2015 | 563,000 | 1,500 | 31,000 | 100,000 | 300,000 | 130,000 | Depending on the flood diversion calculation results of the Ministry of Agriculture and Rural Development. Application of the EPC |
| 7 | Dyke along Saigon river from Vam Thuan to Kinh Lo and culvert under the dyke | Districts 1,4,7, Binh Thanh, Nha Be | Length L=65km, Crest level :+3m | 2012 - 2016 | 8.376,000 | 12,000 | 1.362,000 | 1.500,000 | 2.000,000 | 3.500,000 |  |
| 8 | Vam Thuan tide control culvert | Binh Thanh district | Breadth B = 65m, bottom level : -6m | 2010- 2013 | 280,000 | 30,000 | 150,000 | 98,000 |  |  |  |
| 9 | The remaining segment of Saigon river (from Ngang bridge to Thu Thiem urban area) | Thu Duc district and district 2 | Building the dyke route combined with gentrification, L=8,2 km | 2010- 2015 | 927,000 | 35,000 | 200,000 | 200,000 | 200,000 | 492,000 |  |
| 10 | Dike along the left bank of Saigon river (from Binh Phuoc bridge to Cau Ngang canal) | Thu Duc district | L = 11 344 m, reinforced concrete dyke and 30 culverts of all kinds. | 2009- 2013 | 204,000 | 35,000 | 21,000 | 148,000 |  |  |  |
| 11 | Building 05 tide sluices in Go Dua Ong Dau, Da, Thu Duc, and Cau Duc Nho canals | Thu Duc district | B: from 20m to 30m | 2009- 2012 | 256,000 | 100,000 | 153,000 |  |  |  |  |
| 12 | Dyke along the right bank of Saigon river( from Vam Thuan to Rach Tra ( Nam Rach Tra)) | District 12 and Hoc Mon district | L=66, 80 km of dyke and 219 culverts of all kinds (including 17,26km of dykes along Saigon river and 88 culverts) | 2002- 2011 | 389,350 | 315,350 |  |  |  |  |  |
| 13 | Dyke along the right bank of Saigon river ( from Provincial Route 8 to Rach Tra (Bac Rach Tra)) | Cu Chi District | L=42, 46 km of dyke and 140 culverts of all kinds (including 9,557km of dykes along Saigon river and 53 culverts) | 2002- 2011 | 371,895 | 197,589 |  |  |  |  |  |
| 14 | The right bank of Sai Gon river ( from National Route 8 to Ben Suc) | Cu Chi District | L=17,3km, B=7,5m, Crest level: from +2,8 to +3 Slope coefficient m=1,5 | 2010- 2012 | 541,297 | 280,000 | 251,397 |  |  |  |  |
| 15 | Renovating Phu - Phu My Hung irrigation works | Cu Chi district | L=10,28km, B=7m Crest level: +2,2m; Slope coefficient m=1,5m | 2008- 2011 | 62,008 | 45,488 |  |  |  |  |  |
| 16 | Provide technical assistance for project of flood prevention in Ho Chi Minh city | Ho Chi Minh city | Proposing general measures to minimize flooding in Ho Chi Minh City; improving technical level and managerial capability | 2009-2012 | 500,000 EUR | 308,061 EUR | 108,000 EUR |  |  |  |  |
|  |  |  |  |  | 13,89 | 8,56 | 3,00 |  |  |  |  |

*Note: The exchange rate on December 12, 2010 is 1 Euro = 27779 dong

APPENDIX 2D

LIST OF DREDGED CANALS 
(Enclosed herewith Decision No. 26/2011/QĐ-UBND dated May 14, 2011 of People’s Committee of Ho Chi Minh City)

| No. | List of canals | Investor | Location | Length (m) | Note |
| --- | --- | --- | --- | --- | --- |
| 1. Canals that are under construction |  |  |  |  |  |
| 1 | Nhieu Loc-Thi Nghe canal | Management Board of the project of Ho Chi Minh city environmental sanitation in Nhieu Loc-Thi Nghe basin | Districts 1,3 Tan Binh | 16.000 | Under the project of Ho Chi Minh city environmental sanitation in Nhieu Loc – Thi Nghe basin |
| 2 | Tau Hu-Ben Nghe canal | management board of the project of construction of urban transport works | Districts 1, 5 | 13.320 | Under the project of water environment Improvement of periods 1, 2 |
| 3 | Tham Luong-Ben Cat- Nuoc Len canals | the Service of Agriculture and Rural development | Districts 8, 12, Binh Tan, Tan Binh, Go vap, Binh Thanh, Binh Chanh. | 30.378 | Under the project of drainage and pollution improvement in Tham Luong-Ben Cat-Nuoc Len canals |
| 4 | Ba Bo canal | the Steering Center of Flood Control | Thu Duc district | 2.565 | Under the project of renovating Ba Bo canal |
|  | Total |  |  | 59.698 |  |
| 2. Canals of which investment projects have been set up |  |  |  |  |  |
| 1 | Tan Hoa canal | Management Board of the project of urban Upgrading | Districts 6 | 4.712 | Urban Upgrading Project |
| 2 | Hang Bang canal | management board of the project of construction of urban transport works | Districts 6 | 1.177 | Project of Tieu Hang Bang basin |
| 3 | Dong Tien canal | the Steering Center of Flood Control | Districts 12 | 4.200 | Under the project of dredging and renovating Dong Tien canal |
| 4 | Phan Van Han canal | The Construction Investment Management Board of Binh Thanh District | Binh Thanh district | 1.000 | Renovating Phan Van Han canal |
| 5 | Cau Sa canal | the Service of Agriculture and Rural development | Binh Tan district | 2.800 | Renovating Cau Sa canal |
| 6 | Ong Bup canal | the Steering Center of Flood Control | Binh Tan district | 2.341 | Renovating Ong Bup canal |
|  | Total |  |  | 16.230 |  |
| 3. Canals of which investment projects are being set up |  |  |  |  |  |
| 1 | Bau trau canal | the Steering Center of Flood Control | Districts 6, Binh Tan | 1.572 | Project of renovating Bau Trau canal (from Tan Hoa-Hiep Tan canals) |
| 2 | Dredging Nhay+Ruot Ngua canals | the Steering Center of Flood Control | Districts 6, 8, Binh Tan | 2.469 | Project of dredging Nhay, Ruot Ngua canals |
| 3 | Cau Suoi canal | the Steering Center of Flood Control | Districts 12 | 4.779 | Under the project of dredging and renovating Cau Suoi canal |
| 4 | Hai Vit canal | the Service of Agriculture and Rural development | Districts 12 | 824 | Project of drainage and pollution treatment in Tham Luong - Ben Cat- Nuoc Len canal ( period 2) |
| 5 | Hy Vong canal | the Service of Agriculture and Rural development | Tan Binh district | 1.118 | Project of drainage and pollution treatment in Tham Luong - Ben Cat- Nuoc Len canal ( period 2) |
| 6 | Lien Xa canal | the Steering Center of Flood Control | Binh Tan district | 1.365 | Building box culverts in Lien Ap canal |
| 7 | Luong Beo canal | the Service of Agriculture and Rural development | Binh Tan district | 9.641 | Project of drainage and pollution treatment in Tham Luong - Ben Cat- Nuoc Len canal ( period 2) |
| 8 | KM8 canal | the Service of Agriculture and Rural development | Binh Tan district | 1.043 | Project of drainage and pollution treatment in Tham Luong - Ben Cat- Nuoc Len canal ( period 2) |
| 9 | Ba Tieng canal | the Steering Center of Flood Control | Binh Tan district | 1.954 | Under the project of renovating Ba Tieng canal |
| 10 | Cau Van canal | the Service of Agriculture and Rural development | Go Vap district | 970 | Project of drainage and pollution treatment in Tham Luong - Ben Cat- Nuoc Len canal ( period 2) |
| 11 | Cau Cut canal | the Service of Agriculture and Rural development | Go Vap district | 1.276 | Project of drainage and pollution treatment in Tham Luong - Ben Cat- Nuoc Len canal ( period 2) |
| 12 | Dua canal | the Service of Agriculture and Rural development | Go Vap district | 800 | Project of drainage and pollution treatment in Tham Luong - Ben Cat- Nuoc Len canal ( period 2) |
| 13 | Cau Mat canal | the Service of Agriculture and Rural development | Go Vap district | 1.483 | Project of drainage and pollution treatment in Tham Luong - Ben Cat- Nuoc Len canal ( period 2) |
| 14 | Cau Ngang canal- quarter 4 | The People’s Committee of Thu Duc district | Thu Duc district | 1.200 | Under the project of renovating Cau Ngang canal |
| 15 | Renovating Thu Dao canal | the Steering Center of Flood Control | Binh Chanh district | 4.434 | The project under the master Plan for flood prevention in ho chi minh city ( 1547/QD-TTg) |
| 16 | Renovating Ba Lon canal |  | Districts 7, Nha Be | 7.550 |  |
| 17 | renovating Lung Man canal |  | Binh Chanh district | 2.554 |  |
| 18 | Renovating Xom Cui canal |  | Districts 8, Binh Chanh | 7.638 |  |
| 19 | Renovating Ong Be canal | the Steering Center of Flood Control | Districts 8, Nha Be | 3.324 | The project under the master Plan for flood prevention in ho chi minh city ( 1547/QD-TTg) |
| 20 | Renovating Thay Tieu canal |  | District 7 | 2.600 |  |
| 21 | renovating Can Giuoc river |  | Districts 8, Binh Chanh | 11.750 |  |
| 22 | Rach Tra-Kenh Xang-An Ha-Xang Lon canal |  | Districts 12, Hoc Mon, Binh Chanh, Cu Chi | 38.390 |  |
|  | TOTAL |  |  | 108.734 |  |
| 4. Canals of which investment projects have not been set up |  |  |  |  |  |
| 1 | Dua canal |  | District 2 | 999 | Quarter I / 2011, the Services of Transport, the Service of Agriculture and Rural development completing determining the high edge, the protection corridors of rivers, canals to provide a basis for the districts to determine the clearance scale. From Quarter I / 2011 to quarter III / 2011, localities make plan of policies and route map of clearance of trespass and submit to the People’s Committee. From Quarter I / 2012, building up relocation house fund. |
| 2 | Canal branch along Nguyen Van Huong street |  | District 2 | 1.640 |  |
| 3 | Ba Cua canal |  | District 2 | 3.800 |  |
| 4 | Rach chiec canal branches |  | District 2 | 13.660 |  |
| 5 | Giong Ong To canal branch |  | District 2 | 4.600 |  |
| 6 | Cau Dua canal |  | District 4 | 640 |  |
| 7 | Ben Ngua canal |  | District 7 | 910 |  |
| 8 | Bang canal |  | District 7 | 3.800 |  |
| 9 | Ca Cam canal |  | District 7 | 600 |  |
| 10 | Ba Buom canal |  | District 7 | 2.960 |  |
| 11 | Du canal |  | District 8 | 1.240 |  |
| 12 | Ba Tang canal |  | District 8 | 5.662 |  |
| 13 | Xuyen Tam, Cau Son, Cau Bong canal |  | Binh Thanh district | 11.164 |  |
| 14 | Ung Van Khiem canal |  | Binh Thanh district | 250 |  |
| 15 | Van Thanh canal |  | Binh Thanh district | 2.178 |  |
| 16 | Bui Huu Nghia canal |  | Binh Thanh district | 554 |  |
| 17 | Tan Tru canal |  | Tan Binh district | 1.150 |  |
| 18 | Truong Dai canal |  | Go Vap district | 966 |  |
| 19 | Cau Cut canal, branch 1 |  | Go Vap district | 205 |  |
| 20 | Ba Mieng canal |  | Go Vap district | 2.403 |  |
| 21 | Ong Tong canal branch |  | Go Vap district | 1.447 |  |
| 22 | Ba Ty canal |  | Go Vap district | 531 |  |
| 23 | Nang ( Ba Luu) canal |  | Binh Tan district | 422 |  |
| 24 | Nhay canal ( upstream) |  | Binh Tan district | 1.084 |  |
| 25 | Chua river, branch 1 |  | Binh Tan district | 839 |  |
| 26 | Lo Te canal |  | Binh Tan district | 1.967 |  |
| 27 | Duoi Trau canal |  | Binh Tan district | 1.130 |  |
| 28 | Chua canal |  | Binh Tan district | 580 |  |
| 29 | Muong Le canal |  | Binh Tan district | 1.200 |  |
| 30 | Le Cong Phep canal, branch 2 |  | Binh Tan district | 556 |  |
| 31 | Ba Tieng canal branch |  | Binh Tan district | 1.517 |  |
| 32 | Muoi Xa canal |  | Binh Tan district | 600 |  |
| 33 | Mon canal |  | Thu Duc district | 1.400 |  |
| 34 | Nuoc Trong canal |  | Thu Duc district | 2.600 |  |
| 35 | Ong Lung canal |  | Binh Chanh district | 1.400 |  |
| 36 | Nuoc Len canal branch |  | Binh Chanh district | 1.500 |  |
| 37 | No canal |  | Nha Be district | 1.500 |  |
| TOTAL |  |  |  | 79.654 |  |
| TOTAL (1+2+3+4) |  |  |  | 264.316 |  |

APPENDIX 3

PROGRAM OF COOPERATION IN STUDY OF CLIMATE CHANGE AND HUMAN RESOURCES TRAINING (enclosed herewith Decision No. 26/2011/QĐ-UBND dated May 14, 2011 of People’s Committee of Ho Chi Minh city)

| No. | Name of task/ project | objective | Steering agency | Cooperating agency | capital requirement per year (billion VND) |  |  |  |  | Total cost ( billion dong) | Note |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2011 | 2012 | 2013 | 2014 | 2015 |  |  |
|  | Total |  |  |  | 18,084 | 15,789 | 18,500 | 15,500 | 15,000 | 86,380 |  |
| A | Cooperation in study of climate change |  |  |  | 10,528 | 13,789 | 18,000 | 15,000 | 15,000 | 72,317 |  |
| 1 | Building the Supervisory Control And Data Acquisition (Scada) for testing in Tan Hoa - Lo Gom basin | Remote supervising and acquiring data including communication software | the Service of Science and Technology | the Steering Center of Flood Control | 1,500 |  |  |  |  | 1,500 |  |
| 2 | experimental study on the automatic operation process for Nhieu Loc - Thi Nghe tide control culvert | Designing and building the control network of SCADA for Nhieu Loc-Thi Nghe culvert. | the Service of Science and Technology | the Steering Center of Flood Control | 1,000 | 1,000 |  |  |  | 2,000 |  |
| 3 | Installing the network of monitoring and flood warnings for the entire city | Improve the automation level in flood monitoring | the Steering Center of Flood Control | the Service of Science and Technology |  |  | 10,000 | 10,000 | 10,000 | 30,000 |  |
| 4 | remote sensing integrated solution and GIS serving the task of drainage and flood prevention of Ho Chi Minh City | Serving the management and planning of drainage and flood prevention. | the Steering Center of Flood Control | The Institute of Science and Technology | 1,500 | 1,400 |  |  |  | 2,900 |  |
| 5 | Studying the ability to response to rain events exceeding the design frequency due to climate change for urban drainage systems | Ensuring sustainability and adaptation to climate change | the Service of Science and Technology | the Steering Center of Flood Control | 2,000 | 2,000 |  |  |  | 4,000 |  |
| 6 | Developing, improving the database system of drainage network based on digitalizing and developing a model of management and control of SCADA system | Formulating strategy of management, operation, protection, expansion and construction of new drainage system | the Steering Center of Flood Control | the Service of Science and Technology |  | 5,000 | 5,000 | 5,000 | 5,000 | 20,000 |  |
| 7 | Drawing a map of flood risk warning | Serving warning and handling plans for community | the Steering Center of Flood Control | World Hydraulics Association | 1,000 | 1,000 | 1,000 |  |  | 3,000 |  |
| 8 | feasibility study on minimizing the environmental impact in wastewater management in Ho Chi Minh city | Minimizing environmental impacts in wastewater management and optimizing the management of sludge | the Steering Center of Flood Control | The Government of Spain | 55000 EUR | 50000 EUR |  |  |  | 105000 EUR |  |
|  |  |  |  |  | 1,528 | 1,389 |  |  |  | 2,917 |  |
| 9 | Studying, evaluating the impact on socio-economy of climate change; formulating an integrated strategy to enhance the ability to adapt and respond to flooding; improve the capacity of monitoring and forecasting floods | Ensuring sustainability and adaptation to climate change | the Service of Science and Technology | Relevant Departments, localities. | 2,000 | 2,000 | 2,000 |  |  | 6,000 |  |
| B | Training human resources |  |  |  | 7,556 | 2,000 | 0,500 | 0,500 |  | 14,063 |  |
| 1 | Formulating a plan for development of human resources for drainage sector, wastewater treatment, and flood prevention in Ho Chi Minh City | Meeting the requirement for human resources in the field of urban drainage | the Steering Center of Flood Control | The Service of Internal Affairs. | 0,500 | 0,500 | 0,500 | 0,500 |  | 1,000 |  |
| 2 | Training and improving the management of the model and information applied to the management of water, environment and problems relating to adaptation to climate change | Meeting the requirements for human resources in management and operation of tide control culverts, dykes | the Steering Center of Flood Control | The Government of the Netherlands | 200000 200000 Euro |  |  |  |  | 362267 362267Euro |  |
|  |  |  |  |  | 5,556 |  |  |  |  | 10,063 |  |
| 3 | Studying, expanding training majors in vocational schools in order to train workers in water sector | Serving the requirement for management, operation, maintenance of the drainage system, wastewater treatment plants | The Service of Education and Training | the Steering Center of Flood Control | 0,500 | 0,500 |  |  |  | 1,000 |  |
| 4 | Developing mechanisms and policies, to facilitate strengthening exchange and cooperation in science - technology with international organizations, non-governmental organizations, institutes, universities | Meeting the requirement for training human resources in the field of urban drainage | the Service of Science and Technology | the Steering Center of Flood Control | 0,500 | 0,500 |  |  |  | 1,000 |  |
| 5 | Developing mechanisms and policies to attract staff of research scientists and application of scientific advances, advanced technology of the world in flood prevention | Meeting the requirement for human resources in the field of urban drainage | the Service of Science and Technology | the Steering Center of Flood Control | 0,500 | 0,500 |  |  |  | 1,000 |  |

Note: The exchange rate on December 12, 2010 is 1 Euro = 27779 dong

APPENDIX 4

58 FLOODED STREETS UNTIL THE END OF 2010 (enclosed herewith Decisions No. 26/2011/QĐ-UBND dated May 14, 2011 of the People’s Committee of Ho Chi Minh city)

| TOTAL | No. | STREET NAME | DISTRICT | FLOODING SCOPE |  | IMPLEMENTATION PLAN |  |  | YEAR |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | FROM | TO | CONTENT | PROJECT | INVESTOR | 2011 | 2012- 2015 |
| A.1. CENTRAL AREA ©: 31 points |  |  |  |  |  |  |  |  |  |  |
| 1. BASIN AT THE SOUTH OF NHIEU LOC C1 |  |  |  |  |  |  |  |  |  |  |
| 1 | 1 | Hai Ba Trung | 1 | Tan Dinh market | Tran Quoc Toan | Hastening the progress of the Project of installing drainage culverts on Hai Ba Trung Street | The project of environmental sanitation (Nhieu Loc – Thi Nghe basin)(is being under construction) | The management board of the project of environmental sanitation | X |  |
| 2 | 2 | Mai Thi Luu | 1 | Nguyen Van Giai | Dien Bien Phu | Renovating the drainage system | No project. |  |  | X |
| 2. BASIN AT THE NORTH OF NHIEU LOC (C2) |  |  |  |  |  |  |  |  |  |  |
| 3 | 1 | Nguyen Huu Canh | Binh Thanh | From Ngo Tat crossroads towards Saigon Bridge | Completing the project of Thu Thiem bridge and Nguyen Huu Canh street (from Saigon Bridge to Thu Thiem Bridge). | The project of Thu Thiem Bridge (completed). The project of upgrading Nguyen Huu Canh street (construction has not been started) | Management area Number 1 urban traffic |  | X |  |
| 4 | 2 | Xo Viet Nghe Tinh | Binh Thanh | Dien Bien Phu | Nguyen Cuu Van | Completing the project of installing the drainage culverts on Xo Viet Nghe Tinh street; in order to reduce flood for the area pending the completion of the project, the Steering Center of Flood Control increases the pumping during the project construction. | The project of environmental sanitation (Nhieu Loc – Thi Nghe basin)(is being under construction) | the management board of the project of environmental sanitation |  | X |
| 5 | 3 | Ung Van Khiem | Binh Thanh | Dai Liet Sy | D2 street | To reduce flood in the area pending the completion of the project, connecting the culvert on Ung Van Khiem street to the culvert system Ø800 of the project of environmental sanitation (Nhieu Loc - Thi Nghe basin) on Xo Viet Nghe Tinh to drain water to Son bridge canal. | Project of Binh Trieu Bridge 2 | CII Company |  | X |
| 6 | 4 | Phan Dinh Phung | Phu Nhuan | Kieu bridge | Phu Nhuan market | Completing the project of installing the drainage culverts on Phan Dinh Phung street | The project of environmental sanitation (Nhieu Loc – Thi Nghe basin)( being under construction) | the management board of the project of environmental sanitation | X |  |
| 7 | 5 | Bui Huu Nghia | Binh Thanh | Vu Tung | Bui Huu Nghia bridge | Completing the project of installing the drainage culverts on Bui Huu Nghia street | The project of environmental sanitation (Nhieu Loc – Thi Nghe basin)( being under construction) | the management board of the project of environmental sanitation |  | X |
| 8 | 6 | Vu Tung | Binh Thanh | Bui Huu Nghia | To Vinh Dien school | Completing the project of installing the drainage culverts on Bui Huu Nghia street | The project of environmental sanitation (Nhieu Loc – Thi Nghe basin)( being under construction) | the management board of the project of environmental sanitation |  | X |
| 3. TAN HOA - LO GOM BASIN (C3) |  |  |  |  |  |  |  |  |  |  |
| 9 | 1 | An Duong Vuong | 6 | Ly Chieu Hoang | My Thuan bridge | To reduce flood in the area pending the completion of the project, in 2010, local dredging Ruot Ngua and Bau trau canals in the sluice gate in oder to open the flows reducing flood in the area. | No project. |  |  | X |
| 10 | 2 |  |  | Ba Hom | Mui tau |  |  |  |  | X |
| 11 | 3 | Tan Hoa Dong | 6 | An Duong Vuong | No.151 | To reduce flood in the area pending the completion of 02 above projects, in 2010, dredging and opening flows in Bau Trau and Tan Hoa canals in oder to reduce flood in the area. | No project. |  |  | X |
| 12 | 4 | Phan Anh | Tan Phu | An Duong Vuong | Bon Xa intersection |  |  |  |  | X |
| 13 | 5 | Ba Hom | 6 | Kinh Duong Vuong | An Duong Vuong | Completing the project of installing culverts on Ba Hom street | The project of urban upgrading ( being under construction) | the management board of the project of urban upgrading |  | X |
| 14 | 6 | Truong Cong Dinh | Tan Binh | Truong Chinh | Au Co | Old drainage system | No project. |  |  | X |
| 15 | 7 | Bau Cat | Tan Binh | Truong Cong Dinh | Vo Thanh Trang |  |  |  |  | X |
| 16 | 8 | Dong Den | Tan Binh | Truong Chinh | Tan Hoa canal |  |  |  |  | X |
| 17 | 9 | Au Co | Tan Binh | Thoai Ngoc Hau | Truong Chinh | Completing the project of installing culverts on Au Co street | The project of urban upgrading ( being under construction) | the management board of the project of urban upgrading | X |  |
| 18 | 10 | Luy Ban Bich | Tan Binh | Hoa Binh | Tan Hoa bridge | Completing the project of installing culverts on Luy Ban Bich street |  |  | X |  |
| 19 | 11 | Hoa Binh | 11 | Tan Hoa canal | Lac Long Quan | Completing the project of installing culverts on Hoa Binh street |  |  | X |  |
| 20 | 12 | Nguyen Van Luong | 6 | Cho Lon corner |  | Completing the project of installing culverts on Nguyen Van Luong street |  |  | X |  |
| 21 | 13 | Ba Van | Tan Binh | Nguyen Hong Dao-Au Co |  | No project. |  |  |  | X |
| 4. BASIN IN THE NORTH OF TAU HU (C4) |  |  |  |  |  |  |  |  |  |  |
| 22 | 1 | Ton That Hiep | 11 | Tue Tinh | 3 Thang 2 | To reduce flood in the area, in 2010, completing the project of installing drainage culvert on 3 Thang 2, Nguyen Thi Nho streets, connecting culvert on Ton That Hiep street to the system | The project of environmental sanitation ( period 2) | The management board of construction of urban traffic works |  | X |
| 23 | 2 | Lanh Binh Thang | 11 | Tue Tinh | Lo Sieu | Completing the projects of installing drainage culverts on Le Dai Hanh street; connecting the culverts on Lanh Binh Thang street to the system | The project of environmental sanitation improvement ( completed) | The management board of construction of urban traffic works | X |  |
| 24 | 3 | Tran Hung Dao | 5 | Chau Van Liem | Hoc Lac | No project. |  |  |  | X |
| 25 | 4 | Le Quang Sung | 6 | Mai Xuan Thuong | Minh Phung | No project. |  |  |  | X |
| 26 | 5 | Duong Tu Giang | 5 | Trang Tu | Pham Huu Chi | No project. |  |  |  | X |
| 27 | 6 | Thai Phien | 11 | 3 Thang 2 | Hung Vuong | No project. |  |  |  | X |
| 28 | 7 | Hau Giang | 6 | Thap Muoi | Binh Tien | No project. |  |  |  | X |
| 29 | 8 | Cao Van Lau | 6 | Gia Phu | Bai Say | Completing the project of installing drainage culverts on Pham Dinh Ho - Cao Van Lau streets (from Le Quang Sung street to Tran Van Kieu street). | The project of Hang Bang sub-basin ( being under construction) | the Steering Center of Flood Control continues to monitor | X |  |
| 30 | 9 | Mai Xuan Thuong | 6 | Le Quang Sung | Pham Van Khoe | accelerating the implementation of the project of installing drainage culvert on Mai Xuan Thuong street under the project of water environment improvement in period 2; To reduce flood in the area pending the completion of the project, after the project of installing culverts on Pham Dinh Ho - Cao Van Lau streets (from Le Quang Sung to Tran Van Kieu) is complete , splitting the drainage network to these streets in order to restrict the flowing to Mai Xuan Thuong street. | the project of water environment Improvement -period 2 | the management board of the project of Dong-Tay Highway and water environment | X |  |
| 5. BEN NGHE-DISTRICT 4 BASIN (C5) |  |  |  |  |  |  |  |  |  |  |
| 6. THANH DA BASIN (Ca) |  |  |  |  |  |  |  |  |  |  |
| 31 | 1 | Binh Quoi | Binh Thanh | The People’s Committee of ward 28 | Wharf | Completing the project of upgrading streets and installing drainage system on Binh Quoi street | The project of upgrading streets and installing drainage system on Binh Quoi street ( being under construction) | Management area Number 1 urban traffic | X |  |
| A.2 NORTH (N): 05 points |  |  |  |  |  |  |  |  |  |  |
| 1. THE BASIN IN THE SOUTH OF THAM LUONG (N) |  |  |  |  |  |  |  |  |  |  |
| 32 | 1 | Le Duc Tho | Go Vap | Lang Son parish | Tay Son school | Completing the project of installing drainage system on Le Duc Tho street , under the project of renovation of drainage system outside Tan Hoa - Lo Gom basin | The project of urban upgrading ( the project is being set up) | the management board of the project of urban upgrading |  | X |
|  |  |  |  |  |  | To reduce flood in the area pending the completion of the project, in 2010, connecting culverts on Le Duc Tho street from People’s Committee of ward 13 to Cut bridge and from street No.1 to Pham Van Chieu street. |  |  |  |  |
| 33 | 2 | Le Lai-Le Loi | Go Vap | On Le Lai, Le Loi street | Building a drainage system on Le Lai-Le loi streets | The project of upgrading streets and installing drainage system on Le Loi street | the Steering Center of Flood Control | X |  |  |
| 34 | 3 | Quang Trung | Go Vap | Pham Van Chieu | Cau market | Requesting the Services of Transport for local upgrading of the street surface |  | the Services of Transport |  | X |
| 2. THE BASIN IN THE NORTH OF THE CITY (N) |  |  |  |  |  |  |  |  |  |  |
| 35 | 1 | National Route 1A | 12 | Nguyen Van Qua | Le Thi Rieng | Building a drainage system on National Route 1A (from Le Thi Rieng to Nguyen Van Qua) and having submitting to the Services of Transport in November, 2010 | Building a drainage system on National Route 1A | the Steering Center of Flood Control | X |  |
| 36 | 2 | Nguyen Van Qua | 12 | Truong Chinh | Provincial Route 15 | Completing the project of installing drainage system on Nguyen Van Qua street, under the project of renovation of drainage system outside Tan Hoa - Lo Gom basin. To reduce flood in the area pending the completion of the project, in 2010, connecting culverts D600mm to canals in order to improve drainage in the area. People’s Committee of district 12 handles the trespassing households limiting flows. | The project of urban upgrading | the management board of the project of urban upgrading |  | X |
| A.3. BASIN IN THE NORTHEAST OF THE CITY (NE): 07 points |  |  |  |  |  |  |  |  |  |  |
| 37 | 1 | Kha Van Can | Thu Duc | Duong Van Cam | Post office | The project management board of Thu Duc district accelerates the implementation of the project “dredging Cau Ngang canal”, connect culverts on Kha Van Can street to Cau Ngang canal. To reduce flood in the area pending the completion of the project, in 2010, connecting drainage direction in Cau Ngang canal. | The project of dredging Cau Ngang canal | project management board of Thu Duc district |  | X |
| 38 | 2 | Provincial Route 43 | Thu Duc | Le Thi Hoa | Binh Chieu | Completing the project of upgrading street and installing drainage system on Provincial Route 43 | The project of upgrading street and installing drainage system on Provincial Route 43 ( being under construction) | Management area Number 2 urban traffic |  | X |
| 39 | 3 | Go Dua | Thu Duc | House No.10 | House No.36 | Requesting People’s Committee of Thu Duc district for local upgrading of street surface |  | People’s Committee of Thuc Duc street |  | X |
| 40 | 4 | Thao Dien | 2 | Alley 97 | Sluice gate 8 | People’s Committee of district 2 completes the project of Nguyen Van Huong canal embankments. |  | People’s Committee of district 2 |  | X |
| 41 | 5 | Dang Thi Ranh | Thu Duc | To Ngoc Van | Duong Van Cam | Accelerating the implementation of the project “dredging Cau Ngang canal”, connecting culverts on Kha Van Can, Dang Thi Ranh, Duong Van Cam, Ho Van Tu to Cau Ngang canal. To reduce flood in the area pending the completion of the project, in 2010, connecting drainage direction on Kha Van Can street to cau Ngang canal, dredging Cau Ngang canal | The project of dredging Cau Ngang canal | project management board of Thu Duc district |  | X |
| 42 | 6 | Duong Van Cam | Thu Duc | Kha Van Can | Le Van Tach |  |  |  |  | X |
| 43 | 7 | Ho Van Tu | Thu Duc | Kha Van Can | House No.48 |  |  |  |  | X |
| A.4 THE SOUTHEAST OF THE CITY (SE): 01 point |  |  |  |  |  |  |  |  |  |  |
| 44 | 1 | Do Xuan Hop | 9 | In front of Industry school |  | Completing the project of upgrading, enlarging Do Xuan hop street. |  | Management area Number 2 urban traffic |  | X |
| A.5 THE WEST OF THE CITY (W): 07 points |  |  |  |  |  |  |  |  |  |  |
| 45 | 1 | Kinh Duong Vuong | Binh Tan | Mui tau Phu Lam | An Lac Roundabout | No project. |  |  |  | X |
| 46 | 2 | Truong Vinh Ky | Tan Phu | Tan Son Nhi | Nguyen Xuan Khoat | No project. |  |  |  | X |
| 47 | 3 | Tan Huong | Tan Phu | The entire of street |  |  |  |  | X |  |
| 48 | 4 | Go Dau | Tan Phu | Binh Long | Tan Son Nhi |  |  |  |  | X |
| 49 | 5 | Tan Quy | Tan Phu | Go Dau | House No.161 |  |  |  |  | X |
| 50 | 6 | Tran Dai Nghia | Binh Tan | National Route 1A | Cai Trung bridge | No project. |  |  |  | X |
| 51 | 7 | Ho Hoc Lam | Binh Tan | National Route 1A | Ba Tieng canal | No project. |  |  |  | X |
| A.6 THE SOUTH OF THE CITY (S): 07 points |  |  |  |  |  |  |  |  |  |  |
| 52 | 1 | Nguyen Thi Thap | 7 | Huynh Tan Phat | Le Van Luong | Upgrading, enlarging Nguyen Thi Thap street |  | Management area Number 4 urban traffic | X |  |
| 53 | 2 | Huynh Tan Phat | 7 | Tan Thuan bridge | Phu Xuan bridge | The People's Committee of District 7 clears away the trespass of Ba Buom, Ong Doi, Ben Ngua canals, sluice gates; local dredging Ba Buom, Ong Doi, Ben Ngua canals; increasing the pump to pump rain water; installing box culverts replacing culvert D600 carrying water to Ba Buom sluice gate ; upgrading the surface of Huynh Tan Phat street (from Nguyen Van Quy street to Go O Moi street). | No project. |  |  | X |
| 54 | 3 | Luong Van Can | 8 | Luu Huu Phuoc | House No.57 | Completing the project of embankment and installing the drainage system on Ben Binh Dong and Me Coc streets. | The project of environmental sanitation improvement (being under construction) | the management board of the project of Dong-Tay Highway and water environment | X |  |
| 55 | 4 | Mai Hac De | 8 | Luu Huu Phuoc | Me Coc 2 |  |  |  | X |  |
| 56 | 5 | Le Thanh Phuong | 8 | Mai Hac De | Cat canal |  |  |  | X |  |
| 57 | 6 | Luu Huu Phuoc | 8 | House No.167 | House No.169 |  |  |  | X |  |
| 58 | 7 | Ben Binh Dong | 8 | Bridge No.2 | House No. 325 |  |  |  | X |  |